## Sheet1
ANNEX III
Activity Code | Activity Details | Description | DOE Division Responsible | DOE Officer Responsible | HRDP1 LTTA | Number of Units | Unit Price PGK | Amount PGK | Type of Expenditure | 2012 |  | 2013 |  |  |  | 2014 |  |  |  | 2015
[10 empty] | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
- | INCEPTION | Review & finalisation of HRDP1 Result-Areas and Programme Estimate |  |  |  | 0 | 0 | 0 | None | bar: 2012 Q1
1 | C.1 Management capacity of PNG’s education system for decision-making, planning, assessment, monitoring of education system |  | PPRC | Joe Logha | KE1 |  |  | 6520500
1.1 | 1.1 Strengthen inter-ministerial and inter-departmental dialogue for fully utilising SWAp structures according to ESIP, including NSAs |  | PPRC | Maxton Essy |  |  |  | 1307032 | Direct Expenditure
1.1.1 | 1.1.1 Review of Education Sector Improvement Programme at National and Sub-National levels to understand the progress of the PNG SWAp |  | PPRC | Maxton Essy | KE1 |  |  | 297220 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
a | Develop and Produce Research Materials |  |  |  |  | 0 | 0 | 0 | Direct Expenditure | bar: 2012 Q2
b | Four Province Review of ESIP (Two DOE Personnel, One Vehicle, five days per review) | 4 Missions of 2 people |  |  |  | 3 | 16000 | 48000 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
c | 4 Regional Review Workshops (including 1.1.4, 1.2.1, and 1.3.1) | 2 days, 40 people |  |  |  | 3 | 70000 | 210000 | Direct Expenditure | bar: 2013 Q3
d | 1 National Workshop presenting draft Findings | 30 persons, 1 day |  |  |  | 1 | 30020 | 30020 | Direct Expenditure | bar: 2013 Q3
e | Executive Workshop presenting final Report | 30 persons, Tea & Lunch |  |  |  | 30 | 40 | 1200 | Direct Expenditure | bar: 2013 Q3
f | Production of Final Report | Reports |  |  |  | 200 | 40 | 8000 | Direct Expenditure | bar: 2013 Q3
1.1.2 | 1.1.2 Support to strengthen the institutional arrangements in pursuit of the ESIP goals |  | PPRC | Maxton Essy | KE1 |  |  | 111220 | Direct Expenditure | bar: 2012 Q2 to 2015 Q11
a | ESIP Committee | Monthly Committee Meetings |  |  |  | 32 | 100 | 3200 | Direct Expenditure | bar: 2012 Q2 to 2014 Q9
b | Development of ESIP Manual including Communications, Dialogue and Sensitization strategy |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
c | 1 Regional Workshop presenting draft strategy | 2 days, 40 persons |  |  |  | 1 | 70000 | 70000 | Direct Expenditure | bar: 2013 Q3
d | 1 National Workshop presenting draft strategy | 1 day, 30 persons |  |  |  | 1 | 30020 | 30020 | Direct Expenditure | bar: 2013 Q3
e | Mid-Year Education Sector Review |  |  |  |  | 3 | 0 | 0 | Direct Expenditure | bar: 2013 Q5; 2014 Q9
f | Annual Education Sectior Review | (see 1.2.4) |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3; 2014 Q7; 2015 Q11
g | Research Budget in support of ESIP Committee (see 1.4.3) | Grant |  |  |  | 1 | 0 | 0 | Grant | bar: 2012 Q2 to 2014 Q9
h | Production of ESIP Manual and Procedures | Documents |  |  |  | 200 | 40 | 8000 | Direct Expenditure | bar: 2013 Q3
1.1.3 | 1.1.3 Support for the development of a Single Education Policy/Review of Education Act and Alignment of Education Policies within Legal Framework | Legal Framework & Operationalisation | PPRC | Brian Monie | NKE3 |  |  | 727372 | Direct Expenditure, Grant, Supply Contract | bar: 2012 Q2 to 2014 Q9
a | Tender Dossier for Grant Award to PNG research institution | Tender Dossier |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2012 Q2
b | Grant Award | Lumpsum |  |  |  | 1 | 260552 | 260552 | Grant | bar: 2013 Q3
c | Research Missions - Sub-National Levels (DOE personnel) | 5 Missions for 2 persons for 5 days |  |  |  | 5 | 16000 | 80000 | Direct Expenditure | bar: 2013 Q3 to 2013 Q4
d | Monthly Monitoring Meetings | Multi-Department on-going monthly meetings refreshments |  |  |  | 24 | 100 | 2400 | Direct Expenditure | bar: 2012 Q2 to 2014 Q9
e | Drafting materials (paper, stationary, etc.) | Lumpsum |  |  |  | 1 | 10000 | 10000 | Direct Expenditure | bar: 2012 Q2 to 2014 Q9
f | Regional Consultation Meetings - Draft | 2 days, 40 persons |  |  |  | 4 | 70000 | 280000 | Direct Expenditure | bar: 2013 Q6 to 2014 Q7
g | National Consultation Meetings - Draft | 1 day, 100 persons |  |  |  | 1 | 72620 | 72620 | Direct Expenditure | bar: 2014 Q8
h | Executive Presentation final Report | Tea & Lunch (30 persons) |  |  |  | 30 | 60 | 1800 | Direct Expenditure | bar: 2014 Q9
i | Production of Policy | Publication |  |  |  | 500 | 40 | 20000 | Direct Expenditure | bar: 2014 Q9
1.1.4 | 1.1.4 Support for the strengthening of medium-term expenditure and annual budgeting against sector plans |  | F&A/PPRC | Jack Amenesu | KE1, NKE1 |  |  | 171220 | Direct Expenditure
a | Public Financial Management, Procurement, Medium-Term Budgeting and Expenditure Committee | Monthly Committee Meetings |  |  |  | 32 | 100 | 3200 | Direct Expenditure
b | Review of existing expenditure framework and relationship of medium-term and annual planning/budgeting at national and sub-national levels |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
c | 4 Province Review of budgeting and practises (Two DOE Personnel, One Vehicle, five days per review) | 3 Missions of 2 people |  |  |  | 3 | 16000 | 48000 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
d | Strengthening/ further development of a draft medium-term expenditure framework and guidelines |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3 to 2013 Q4
e | Regional Consultation of the draft medium-term expenditure framework and guidelines | 1 Regional Consultation of 40 participants, 2 days |  |  |  | 1 | 70000 | 70000 | Direct Expenditure | bar: 2013 Q5
f | National Consultation of the draft medium-term expenditure framework and guidelines | 1 National Consultation of 30 participants, 1 days |  |  |  | 1 | 30020 | 30020 | Direct Expenditure | bar: 2013 Q5
g | Implementation of final medium-term expenditure framework | Launch (Lump-sum) |  |  |  | 1 | 20000 | 20000 | Direct Expenditure | bar: 2013 Q5 to 2015 Q12
1.2 | 1.2 Strengthen performance M&E system at all levels |  | PPRC | James Agigo |  |  |  | 1452140 | Direct Expenditure
1.2.1 | 1.2.1 Review of Monitoring and Evaluation structures at National and Sub-National level |  | PPRC | James Agigo | NKE2 |  |  | 52200 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
a | Develop and Produce Research Materials |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
b | Three Provincial Reviews of M&E Framework and practises (Two DOE Personnel, One Vehicle, five days per review) | 3 Missions of 2 people |  |  |  | 3 | 16000 | 48000 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
c | Executive Workshop presenting Report of Review | Tea & Lunch (30 persons) |  |  |  | 30 | 40 | 1200 | Direct Expenditure | bar: 2013 Q3
d | Production of Final Report | Reports |  |  |  | 100 | 30 | 3000 | Direct Expenditure | bar: 2013 Q3
1.2.2 | 1.2.2 Strengthen Educstion Sector M&E system |  | PPRC | James Agigo | NKE2 |  |  | 565740 | Direct Expenditure, Supply Contract, Grant
a | Research and Monitoring and Evaluation Committee | Monthly Committee Meetings |  |  |  | 32 | 100 | 3200 | Direct Expenditure
b | Support to Finalisation for M&E Framework and supporting M&E Policy |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3
c | Regional Consultation of M&E Framework and Policy (50 participants at Regional level) | 2 day, 40 person |  |  |  | 3 | 110840 | 332520 | Direct Expenditure | bar: 2013 Q3
d | National Consultation of M&E Framework and Policy | 1 day, 30 persons |  |  |  | 1 | 30020 | 30020 | Direct Expenditure | bar: 2013 Q3
e | Production of Final M&E Framework and Policy | Publication |  |  |  | 10000 | 20 | 200000 | Supply Contract | bar: 2013 Q3
f | Sub-national M&E HR Capacity Building | see 1.4.1 |  |  |  | 0 | 0 | 0 | Supply Contract, Grant | bar: 2013 Q5 to 2014 Q8
1.2.3 | 1.2.3 Annual Education Sector Reviews (AESR) and support to decision-making at all levels |  | PPRC | James Agigo | NKE2 |  |  | 834200 | Direct Expenditure, Supply Contract
a | Development of AESR Committee (sub-committee to ESIP Committee 1.1.2) | Monthly Committee Meetings |  |  |  | 32 | 100 | 3200 | Direct Expenditure
b | Development of AESR Manual |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3
c | Production of AESR Materials | Printing/Copying (300 per AESR) |  |  |  | 600 | 30 | 18000 | Supply Contract | bar: 2013 Q3; 2014 Q7; 2015 Q11
d | Provincial AESR Missions | 6 person 3-day missions, 4 per AESR for 2 years |  |  |  | 8 | 34800 | 278400 | Direct Expenditure | bar: 2013 Q3; 2014 Q7; 2015 Q11
e | National Workshops | 3 day National Workshop with three presentation rooms for 200 people |  |  |  | 2 | 246300 | 492600 | Direct Expenditure | bar: 2013 Q3; 2014 Q7; 2015 Q11
f | Production of Final AESR Report | Printing/Copying (300 per AESR) |  |  |  | 900 | 30 | 27000 | Supply Contract | bar: 2013 Q3 to 2013 Q4; 2014 Q7 to 2014 Q8; 2015 Q11 to 2015 Q12
g | Dissemination of AESR Report and School and District Census Reports | Lumpsum |  |  |  | 3 | 5000 | 15000 | Direct Expenditure | bar: 2013 Q4; 2014 Q8; 2015 Q12
1.3 | 1.3 Strengthen the management capacities of education administrators at sub-national levels |  | F&A | Etwin Apai |  |  |  | 515340 | Direct Expenditure
1.3.1 | 1.3.1 Review of Public Financial Management and Procurement practises at Sub-national levels (province, district and schools) |  | F&A | Jack Amenesu | KE1, NKE1 |  |  | 82220 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
a | Develop and Produce Research Materials |  |  |  |  | 0 | 0 | 0 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
b | Four Province Review of PFM and Procurment (Four DOE Personnel, One Vehicle, five days per review) | 4 Missions of 2 people |  |  |  | 3 | 16000 | 48000 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
c | 1 National Workshop presenting draft Findings | 1 day, 30 persons |  |  |  | 1 | 30020 | 30020 | Direct Expenditure | bar: 2013 Q3
d | Executive Workshop presenting final Report | Tea & Lunch (30 persons) |  |  |  | 30 | 40 | 1200 | Direct Expenditure | bar: 2013 Q3
e | Production of Final Report | Reports |  |  |  | 100 | 30 | 3000 | Direct Expenditure | bar: 2013 Q3
1.3.2 | 1.3.2 Strengthen system capacity for sector public financial management and procurement |  | F&A | Jack Amenesu | KE1, KE2, NKE1 |  |  | 433120 | Direct Expenditure, Supply, Service, Grant | bar: 2012 Q2 to 2014 Q9
a | Public Financial Management, Procurement, Medium-Term Budgeting and Expenditure Committee | see 1.1.4 |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2012 Q2 to 2014 Q9
b | Development of sector financial management manual and templates for all levels |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3 to 2013 Q4
c | Testing of sub-national manual and templates | 2 missions of 3 persons for 3 days |  |  |  | 2 | 14050 | 28100 | Direct Expenditure | bar: 2013 Q4
d | Finalisation of sector financial management and procurement manual and templates for all levels; development of training materials |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q4
e | Regional Consultation Workshop | 2 day, 40 person |  |  |  | 1 | 70000 | 70000 | Direct Expenditure | bar: 2013 Q4
f | National Consultation Workshop | 1 day, 30 persons |  |  |  | 1 | 30020 | 30020 | Direct Expenditure | bar: 2013 Q4
g | Production of PFM and Procurement Materials | Printing (School=15,000; Province and District 250) |  |  |  | 15250 | 20 | 305000 | Supply Contract | bar: 2013 Q5
h | Sub-national PFM and Procurement HR Capacity Building | see 1.4.1 |  |  |  | 1 | 0 | 0 | Service Contract, Grant | bar: 2013 Q6 to 2014 Q9
1.3.3 | 1.3.3 Support to Leadership and Management Competency Framework at school level |  | S&G | Peter Kants | KE2 |  |  | 0 | Direct Expenditure, Grant | bar: 2012 Q2 to 2015 Q11
a | Support to Standards & Guidance and Techer Education Divisions in finalisation of Head Teacher Training Materials | Lumpsum |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2012 Q2 to 2013 Q4
b | Testing of Training Materials | Lumpsum |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q4
c | Support to the revitalisation of school clusters for the prupose of in-service training |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q4
d | Head Teacher Training | see 1.4.1 |  |  |  | 1 | 0 | 0 | Service Contract, Grant | bar: 2013 Q6 to 2015 Q11
1.4 | 1.4 Strengthen capacity of the PNG Education Sector utilising research and academic institutions in management training |  | S&G | Peter kants |  |  |  | 3245988 | Service Contract, Direct Expenditure, Grant
1.4.1 | 1.4.1 Provincial, District and Deconcentrated Officer Capacity Building | Sector communication, expenditure, PFM, Procurement and M&E Capacity Building | S&G | Peter kants | KE2 |  |  | 1733488 | Service Contract, Supply Contract, Direct Expenditure | bar: 2013 Q3 to 2014 Q10
a | Award of Grant | Tender Dossier |  |  |  | 1 | 151988 | 151988 | Grant | bar: 2013 Q3
b | Training of Trainers (2 persons per province) | 42 persons for 5 days, twice during project |  |  |  | 2 | 204800 | 409600 | Direct Expenditure | bar: 2013 Q5; 2014 Q9
c | Capacity Building Training | Training of 5 persons in 21 Provinces and 5 persons in 87 Districts for 5 days, twicw during project |  |  |  | 42 | 26950 | 1131900 | Service Contract, Direct Expenditure | bar: 2013 Q5; 2014 Q9
d | Monitoring & Evaluation | 10, 3 day missions to monitor training at sub-national level |  |  |  | 10 | 4000 | 40000 | Direct Expenditure | bar: 2013 Q5 to 2013 Q6; 2014 Q9 to 2014 Q10
1.4.2 | 1.4.2 School Level Capacity Building |  | TE | Dominica Philip | KE2, NKE2 |  |  | 1251948 | Service Contract, Supply Contract, Direct Expenditure | bar: 2013 Q3 to 2014 Q9
a | Award of Grant | Tender Dossier |  |  |  | 1 | 94420 | 94420 | Grant | bar: 2013 Q3
b | Training of Trainers (4 persons per region (n-16)) | 10 days training of 16 persons in POM |  |  |  | 1 | 161000 | 161000 | Direct Expenditure | bar: 2013 Q4; 2014 Q8
c | Pilot of Leadership and Management Competency Framework Training, including PFM and M&E - Training of Head Teachers (n=tbd) | Training of Head Teachers for 10 days per 4 regions (number tbd) |  |  |  | 1 | 916528 | 916528 | Direct Expenditure | bar: 2013 Q5; 2014 Q9
d | Monitoring & Evaluation | 20, 3 day missions to monitor training at sub-national level |  |  |  | 20 | 4000 | 80000 | Direct Expenditure | bar: 2013 Q4 to 2013 Q5; 2014 Q8 to 2014 Q9
1.4.3 | 1.4.3 Involve PNG research and academic Institutoins in studies on education |  | PPRC | James Agigo | KE1, KE2 |  |  | 260552 | Grant
a | Provision for research (to be determined) | See 1.1.2 |  |  |  | 1 | 260552 | 260552 | Grant
2 | C.2 Pedagogical and management skills of basic education school teachers improved |  | TE | Walipe Wingi | KE2 |  |  | 1323470
2.1 | 2.1 Carry out immediate skills training for TTC lecturers with a prime focus on pedagogy (OBE requirements, ICT, etc) and management |  | TE | Dominica Philip |  |  |  | 1323470
2.1.1 | 2.1.1 Needs analysis of TTCs and TTC lecturers |  | TE | Dominica Philip | KE2 |  |  | 79774 | bar: 2012 Q2 to 2013 Q3
a | Design, testing and development of TNA based upon agreed set of competencies for TTC Lecturers; design and development of qualification criteria for identification of TTC Trainers of Lecturers | NCD based. Lump-sum |  |  |  | 1 | 5154 | 5154 | Direct Expenditure | bar: 2012 Q2
b | TNA of 5 TTC | 4 persons for five days |  |  |  | 3 | 14500 | 43500 | Direct Expenditure | bar: 2012 Q2 to 2013 Q3
c | Identification of TTC Trainers of Lecturers | Proposed by TTC against criteria (3 per college) n=42 |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3
d | Workshop presenting TNA Report | 1 day of 30 people including 14 TTC Principals in Port Moresby |  |  |  | 1 | 29120 | 29120 | Direct Expenditure | bar: 2013 Q3
e | TNA Report | Publication (n=100) |  |  |  | 100 | 20 | 2000 | Direct Expenditure | bar: 2013 Q3
2.1.2 | 2.1.2 Produce in-service training materials for TTC lecturers |  | TE | Dominica Philip | KE2 |  |  | 91320 | bar: 2013 Q3 to 2013 Q5
a | Review of "Lecturer Associate Programme" against developed competency framework for TTC Lecturers |  |  |  |  | 1 | 0 | 0 | Direct Expenditure | bar: 2013 Q3
b | Update and further development of "Lecturer Associate Programme" by Inter-College Subject Committees, PNGEI and DOE | Convening of Inter-College subject Committees (12 flights, 36 per diem/accommodation) |  |  |  | 1 | 41200 | 41200 | Direct Expenditure | bar: 2013 Q3 to 2013 Q4
c | Workshop presenting Draft "Lecturer Associate Programme" | 1 day of 30 people including 14 TTC Principals in Port Moresby |  |  |  | 1 | 29120 | 29120 | Direct Expenditure | bar: 2013 Q4
d | Finalisation of "Lecturer Associate Programme", including certification reapproval |  |  |  |  | 0 | 0 | 0 | Direct Expenditure | bar: 2013 Q4 to 2013 Q5
e | Production of Materials | 280 Lecturers x 2 years plus 40 spare |  |  |  | 300 | 50 | 15000 | Supply Contract | bar: 2013 Q5
f | Production of CD-ROM |  |  |  |  | 600 | 10 | 6000 | Direct Expenditure | bar: 2013 Q5
2.1.3 | 2.1.3 Conduct training of 42 Trainers of Trainers (Port Moresby) |  | TE | Dominica Philip | KE2 |  |  | 535248 | bar: 2013 Q6 to 2014 Q10
a | Grant - PNGEI to host and conduct residential training | 3 week training program for 42 individuals |  |  |  | 42 | 12744 | 535248 | Direct Expenditure, Grant | bar: 2013 Q6; 2014 Q10
2.1.4 | 2.1.4 Conduct nationwide in-service training for TTC lecturers |  | TE | Dominica Philip | KE2 |  |  | 536128 | bar: 2014 Q7 to 2015 Q11
a | TTC-based Training of Lecturers (Year 1 and Year 2) | 14 x 20 person courses for 18 days for two years |  |  |  | 14 | 34902 | 488628 | Direct Expenditure | bar: 2014 Q7; 2015 Q11
b | TTC Training of Lecturers Monitoring | 20 missions for one person for 5 days |  |  |  | 10 | 4750 | 47500 | Direct Expenditure | bar: 2014 Q7; 2015 Q11
2.1.5 | 2.1.5 Conduct impact assessment mid year after training for both Year 1 and Year 2 |  | TE | Dominica Philip | KE2 |  |  | 81000 | bar: 2013 Q3 to 2015 Q12
a | Development of Impact Assessment Tools - self-assessment and external assessment |  |  |  |  | 1 | 0 | 0 | bar: 2013 Q3 to 2013 Q4
b | Production of Tools | 14 colleges, 10 tool kits per college, for 2 years |  |  |  | 140 | 100 | 14000 | Direct Expenditure | bar: 2013 Q4
c | Impact Assessment missions | 14 missions for 2 persons for 3 days |  |  |  | 10 | 6700 | 67000 | Direct Expenditure | bar: 2014 Q7 to 2014 Q8; 2015 Q11 to 2015 Q12
3 | C.3 Access to Teachers to Pre- and In-Service Training Improved |  | TE | Walipe Wingi | KE1 |  |  | 16715600
3.1 | Improve Infrastructure in Teacher Training Colleges |  | PPRC/TE | Madako Suari | KE1 |  |  | 13027600
3.1.1 | 3.1.1 Construct and equip classrooms and other school facilities | New infrastructure and fittings at TTC |  |  |  | 1 | 13027600 | 13027600 | Works, Services (Specific Commitments) | bar: 2012 Q1 to 2014 Q9
3.2 | Enhance access for identified trainee teachers coming from and returning to remote and underserviced communities |  | TE | Dominica Philip | KE1 |  |  | 3688000
3.2.1 | 3.2.1 Identify communities where availability of teachers is scarce |  |  |  |  | 1 | 0 | 0
3.2.2 | 3.2.2 Provide scholarships for teachers from remote communities | 250 Scholarships (219 2 year and 31 1 year) |  |  |  | 1 | 3688000 | 3688000 | Direct Expenditure | bar: 2012 Q1 to 2014 Q8