DEPARTMENT OF EDUCATION

The National Authorizing Officer of the Government of Papua New Guinea (Contracting Authority)

The Department of Education of the Government of Papua New Guinea

(Beneficiary and Implementation)

The European Union

Human Resource Development Programme, Phase 1 (HRDP1)

Financing Agreement NoPG/FED/21643

INCEPTION REPORT

Version: Draft Final

Date: 22nd October 2012

Service Contract: Eurecna S.p.A Consortium - EuropeAid/130/786/D/SER/PG

| Programme Title: | Human Resource Development Programme Phase 1 |
| --- | --- |
| Project Number: | PG/FED/21643 |
| Country: | Papua New Guinea |
| Lead Contractor: | Eurecna S.p.A. Via della Pila 3/A 30175 Venezia Marghera, Italy |
| Contact Person: | Ms. Romina Carrer Tel: +39 041 2919411 Fax: +39 041 5322465 E-mail: carrer@eurecna.it |
| In partnership with: | Crescendo UK Ltd. & WYG |
| Date of report: | Draft 24th August 2012 |
| Reporting period: | Inception Period (18th June to 24th August 2012) |
| Submitted to: | National Authorizing Officer, Hon. Minister of National Planning and Monitoring |
| Beneficiary: | Secretary of Education Department of Education PO Box 446, Waigani NCD, Papua New Guinea |
| Author of report: | Carlton Aslett, Long-Term Technical Assistance Team Leader Tel: +675 7116 1471 Tel: +675 7222 8230 Email: carlton@aslett.eu |

Mr. Joe Logha					Mr. Carlton Aslett

Asst. Secretary, Planning and Policy 		Team Leader, HRDP1 Long-Term Technical

Assistance

Project Manager 		   		Team Leader

For the Beneficiary

Eurecna S.p.A. would be happy to answer any queries raised in connection with this report                                                              or to provide further information if necessary.

Table of Contents

Table of Contents	iii

Annexes	iv

Glossary of Acronyms and Abbreviations	v

1	Background	1

1.1	Activities carried out during the inception phase	2

2	Programme Synopsis	3

2.1	Overall Objectives	3

2.2	Programme Purpose	3

2.3	Expected Results	3

2.4	Planned Activities	4

2.4.1	Result-Area 1 - Management capacity of PNG education system strengthened for decision-making, planning, assessment, monitoring	4

2.4.2	Result-Area 2 - Pedagogical and management skills of basic education school teachers improved	4

2.4.3	Result-Area 3 - Access of teachers to pre-service and in-service training improved	5

2.5	Programme Budget	6

2.6	Programme Partnership	7

3	Plan of Operations	8

3.1	Inception Findings and Overall work plan for the programme	8

3.1.1	Logical Framework	8

3.1.2	Result-Area 1: Management capacity of PNG education system strengthened for decision-making, planning, assessment, monitoring	11

3.1.3	Result-Area 2 - Pedagogical and management skills of basic education school teachers improved	20

3.1.4	Result-Area 3: Access of teachers to pre-service and in-service training improved	22

3.1.5	HRDP1 Indicative Budget	26

3.2	Plan of operations for the next period	27

3.2.1	Result-Area 1: Management capacity of PNG education system strengthened for decision-making, planning, assessment, monitoring	27

3.2.2	Result-Area 2: Pedagogical and management skills of basic education school teachers improved	28

3.2.3	Result-Area 3: Access of teachers to pre-service and in-service training improved	28

4	Implementation Arrangements	28

4.1	Project Management	28

4.2	Logistics	29

4.3	Reporting	29

4.4	Coordination	30

4.5	Resources and Budget	31

4.5.1	Human resources	31

4.5.2	Input Utilisation	32

4.5.3	Incidental Expenditure	33

4.6	Team Management	33

4.7	Financial Management	34

4.8	Project Visibility	35

5	Monitoring and Evaluation	35

5.1	Definition of indicators	35

5.2	Monitoring	38

6	Update on Assumptions and Risks	38

6.1	Assumptions	38

6.2	Risks and flexibility	39

7	Planning to ensure sustainability	40

7.1	Appropriate Ownership	40

7.2	Appropriate Systems and Processes	40

7.3	Social Aspects	40

7.4	Programme Management Capacity	40

7.5	Exit Strategy	40

Annexes

| Annex I – not annexed | Universal Basic Education Plan 2010-2019 |
| --- | --- |
| Annex II – see link “Financing Agreement” | Financing Agreement No PG/FED/21643 |
| Annex III | HRDP1 Work Plan |
| Annex IV | Eurecna S.p.A. Consortium Technical Proposal |
| Annex V | HRDP1 Amended Log-Frame |
| Annex VI - not annexed | Indicative Terms of Reference for Non-Key Experts |
| Annex VII | Indicative Annex 3, Programme Estimate 1 Addendum 1 |
| Annex VIII | Terms of Reference – HRDP1 Institutional Bodies |

Glossary of Acronyms and Abbreviations

| AESR | Annual Education Sector Review | NAO | National Authorizing Officer |
| --- | --- | --- | --- |
| AuSAID | Australian Agency for International Development | NAO-SU | National Authorizing Officer - Support Unit |
| CDF | Capacity Development Facility | NCD | National Central District |
| DNPM | Department of National Planning and Monitoring | NEB | National Education Board |
| DOE | National Department of Education | NGO | Non Government Organization |
| DOF | Department of Finance | NKE | Non Key Expert |
| DP | Development Partner | OVI | Objectively Verifiable Indicator |
| EC | European Commission | PAF | Performance Appraisal Framework |
| EDF10 | European Development Fund 10 | PFM | Public Financial Management |
| EDF11 | European Development Fund 11 | PGK | Papua New Guinea Kina |
| EDF9 | European Development Fund 9 | PNG | Papua New Guinea |
| EHP | East Highlands Province | PNG-ARNet | PNG Academic Research Network |
| EMIS | Education Management Information System | PNGEI | Papua New Guinea Education Institute |
| ENB | East New Britain | RA | Result-Area |
| ESIP | Education Sector Improvement Programme | SDA | Seventh Day Adventist |
| ETHRDP | Education Training and Human Resource Development Programme | SPSP | Sector Policy Support Programme |
| EU | European Union | SWAp | Sector Wide Approach |
| EUR | Euro | TA | Technical Assistance |
| GoPNG | Government of Papua New Guinea | tbd | To be determined |
| HRDP1 | Human Resource Development Programme Phase 1 | TL | Team Leader |
| HRDP1 | Human Resource Development Programme Phase 2 | TMT | Top Management Team |
| ICT | Information Communication Technology | TOR | Terms of Reference |
| JICA | Japanese International Cooperation Agency | TTC | Teacher Training College(s) |
| KE | Key Expert | TWG | Technical Working Group |
| LTTA | Long-Term Technical Assistance | UBE | Universal Basic Education Plan (2010-2019) |
| M&E | Monitoring and Evaluation | VSO | (UK) Volunteer Services Overseas |
| MTEF | Medium Term Expenditure Framework | WNB | West New Britain |

# Background

The Inception Phase of the Long-term Technical Assistance contract to Human Resource Development Programme (Phase 1) commenced on 18th June 2012. Key Expert No 1, Team Leader, arrived in country on 20th June 2012, followed by the Eurecna representatives on 24th June 2012.

The findings from the inception phase are that the state of education in Papua New Guinea remains more or less unaltered since the development of the Eurecna HRDP1 Technical Proposal submitted in 2012. As such, the Technical Proposal remains valid and this report provides updates to the implementation of HRDP1 based upon the expansion of our knowledge of PNG during the past weeks.

Policy Framework

In 2009, the long-term Papua New Guinea development strategy, Vision 2050 was launched, addressing PNG low social and economic indicators. The strengthening of service delivery mechanisms at sub-national levels is an integral goal. The strategic Human Capital Development goal is to progress from position 148 (of 182 countries) of the Human Development Index (HDI) to position 50 by 2050. DSP30 and MTDP15 provide strategic direction and key indicators to sector plans.

The Education Sector Strategic Plan 2030 and Education Corporate Plan 2011 – 2015 link to the above and are detailed through the Universal Basic Education Plan (UBE) 2010 - 2019 and the National Education Plan (NEP). The UBE goal is to achieve universal, free basic education. Secondary education is addressed under NEP.

Strategic to the above is the development of a Sector Wide Approach (SWAp). The Education Sector Improvement Programme (ESIP) commenced in 2009 and is a joint programme between PNG and development partners, led by the Department of Education (DOE). A core ESIP goal is for all significant funding/support for the education sector to align under a single policy and expenditure programme, under PNG government leadership.

The ambitious education goals of PNG require an improved trend of PNG funding, in particular to support school infrastructure and supplies and teacher training and deployment at all levels. Education is one of the key sectors under PNG Development Strategic Plan 2010 – 2030 and Medium Term Development Plan 2011 -2015. PNG and Development Partners (DP) in recent years have concentrated heavily on basic education, culminating in the launch of free and universal basic education. The impact has been considerable but has resulted in insufficient capital and human resource to meet the growing demand. This further places strain upon the administration and management of the entire sector.

Role of HRDP1

The Human Resource Development Programme Phase 1 (HRDP1) is the first of two phases in support of Papua New Guinea education sector, focusing upon UBE and ESIP. Both plans/programmes were ambitious and have encountered difficulties in achieving their goals due to budgetary constraints (UBE) and technical resource (ESIP). The UBE plan called for considerable capital (infrastructure) and human resource development, which were easily beyond the available national revenues and development partner forecast for education. The ESIP received strong support to provide secretariat services during the first year of operations with the agreement that these services would be taken over by the Department of Education in year two. Unfortunately, the DOE did not have capacity to maintain this level of service upon cessation of support resulting in the marginalisation of ESIP as a programme, despite the initial good progress.

HRDP1 will this provide technical and financial resource to support the continued implementation of UBE and resurrection of ESIP as the vehicle for achieving an education SWAp. The budgetary support by HRDP1 for UBE is limited and to maximise its impact, DOE supported by LTTA will try to use these funds as catalysts for counterpart funding (National, Sub-National and Church Agency). For ESIP, many initiatives have commenced but lay incomplete and not fully utilised, and HRDP1 will look to support DOE to review, strengthen and complete activities, such as the ESIP Manual, Monitoring & Evaluation Framework and Policy and Medium-Term Expenditure Framework.

## Activities carried out during the inception phase

The following activities were carried out during the inception phase:

| 1 | Formal opening meetings with beneficiary (Department of Education), Contracting Authority (National Authorizing Officer, represented by the Support Unit) and Delegation of the European Union to Papua New Guinea (week commencing 24th June 2012). |
| --- | --- |
| 2 | One-to-One and Group interviews with Department of Education Officers |
| 3 | Participation at the Annual 2012 Senior Education Officer Conference, West New Britain |
| 4 | One-to-One interviews with Provincial Education Advisors |
| 5 | Review and comments to the HRDP1 scoping and Design and Supervision report |
| 6 | Review and re-writing of HRDP1 Works Design and Supervision Terms of Reference and Annexes |
| 7 | Participation in discussions regarding means of resolution of HRDP1 Infrastructure scope |
| 8 | Field visit to Bomana Teacher Training College (TTC) |
| 9 | Design and development of HRDP1 Scholarship Agreement and Annexes (reporting and invoicing) |
| 10 | Support to TTC development of reports and invoices |
| 11 | Support to DOE EDF10 Imprest Team & development of procedures and tools |
| 12 | Support to DOE EDF9 Imprest Teams in regard to closure |
| 13 | Development of Terms of Reference for HRDP1 Steering Committee, Technical Focal Group and Component Focus Points |
| 14 | HRDP1 LTTA Operational Set-up |
| 15 | Support to procedures for replacement of KE2 |
| 16 | Review and drafting of addendum to HRDP1 Programme Estimate 1 |
| 17 | Review of HRDP2 Identification Fiche as a result of QSG comments |

# Programme Synopsis

Human Resource Development Programme Phase I (HRDP1) is the first of two phases of European Union support targeting the further development of capacity to manage and deliver education services in Papua New Guinea. This programme, as formulated in 2010, includes the following:

## Overall Objectives

The overall objective of HRDP1 is as follows:

To promote the development of PNG human resource development in the education sector

## Programme Purpose

The purpose of HRDP1 is two-fold:

- To support the implementation of the Universal Basic Education (UBE) Plan (2010-19)

- To strengthen the education Sector Wide Approach (SWAp)

## Expected Results

The HRDP1 design is aligned with the Government education sector programme by addressing three expected results related to management, quality of education, and access:

- Management capacity of PNG education system improved;

- Pedagogical and management skills of basic education school teachers improved; and

- Access of teachers to pre-service and in-service training improved.

Improvement of educational management capacity is captured at top management level (strengthening SWAp structures through inter-ministerial and inter-departmental dialogue) and sub-national levels, with a crosscutting focus on enhancing capacities for performance monitoring at all levels.

Based on the UBE intervention tree, the enhancement of quality of education is targeted through strengthening Human Resources capacities and training structures for pre-service and in-service teacher training, whereby Teacher Training College lecturers are regarded as multipliers for subsequently improving pedagogical and management skills of primary school teachers.

In addition, improved access to teacher training is covered through the provision of infrastructure and scholarships, particularly for teachers coming from remote areas (equity aspect).

## Planned Activities

The planned activities as detailed in Financing Agreement No PG/FED/21643 and presented in the Eurecna S.p.A. Consortium Technical Proposal are as follows:

### Result-Area 1 - Management capacity of PNG education system strengthened for decision-making, planning, assessment, monitoring

Result-Area 1 is broken down into four core Activities:

1.1 Strengthen inter-ministerial and inter-departmental dialogue for fully utilizing SWAp structures according to ESIP, including NSA

1.2 Strengthen performance M&E system at all levels

1.3 Strengthen the management capacities of education administrators at sub-national levels

1.4 Strengthen involvement of Papua New Guinea research and academic institutions in management training

Activity 1.4 crosscuts activities 1.2 and 1.3 and is not strictly an activity. As such is it replaced by the following activity:

1.4 Strengthen capacity of the PNG Education Sector utilizing research and academic institutions for management training

With the above modification, each activity is broken down into implementable sub-activities, with clear outputs and goals, in support of the overall purpose and objectives. These are presented in Chapter 3.

### Result-Area 2 - Pedagogical and management skills of basic education school teachers improved

Result-Area 2 is broken down into three core Activities:

2.1 Carry out immediate skills training for TTC lecturers with a prime focus on pedagogy and management

2.2 Strengthen decentralised and distance-mode training structures for primary school teachers and their professional development, particularly those in remote and underserviced areas

2.3 Develop/strengthen networks of TTC and universities involved in primary and lower secondary teacher training

Result-Area 2 supports in-service and pre-service teacher training and shares a budget line with Result-Area 3 pre-service teacher training support (Scholarships). A Programme Estimate in support of Scholarships was agreed in March 2012 and a provision of PGK 3,708.000 or EUR 1,377,637 was made for the training of 219 students (Years 1 and 2) and 31 Year 2 students (beneficiaries of one years support under the EDF9 Education Training and Human Resource Development Programme (ETHRDP)). The provision equals 62 per cent of the total provision for teacher training. The remaining EUR 822,362 is insufficient to execute the three activities under Result-Area 2. As such, following the advice of DOE, Result-Area 2 will prioritise the further development of TTC Lecturers. The resultant program will thus be:

2.1 Carry out immediate skills training for TTC lecturers with a prime focus on pedagogy and management

The activity is broken down into implementable sub-activities, with clear outputs and goals, in support of the overall purpose and objectives. These are presented in Chapter 3.

### Result-Area 3 - Access of teachers to pre-service and in-service training improved

Result-Area 3 is broken down into two core activities:

3.1 Improve infrastructure in Teacher Training Colleges

3.2 Enhance access for identified trainee teachers coming from and returning to remote and underserviced communities

Result-Area 3 commenced activities prior to the arrival of the Long-Term Technical Assistance (LTTA): for 3.1, a Framework contract (EuropeAid/127054/C/SER/multi) for the scoping of infrastructure support and development of Terms of Reference for the Design and Supervision of Infrastructure was carried out in February/ March 2012; and for 3.2, scholarships students were identified and Education Diploma classes commenced in alignment with the PNG academic schedule.

Activities for both initiatives have experienced difficulties, requiring LTTA support. The Framework contractor failed to deliver a concise, understandable report and TOR resulting in the re-writing and re-budgeting of the Design and Supervision TOR and question marks regarding the basis for the scope of the infrastructure support. With no data deposited with the beneficiary upon completion, time is required to collect new data to inform the strategic investment decision for Teacher Training Colleges.

For Scholarships, no agreements had been made between scholarship students, institutions and DOE. No reporting and payment structure had been agreed between DOE and Institutions. With support, DOE has now developed agreements between parties and a structure for operating with the institutions that will provide the training and administrate the scholarships.

Chapter 3 provides a break down of activities into implementable sub-activities, with clear outputs and goals, in support of the overall purpose and objectives.

## Programme Budget

The overall Programme Budget as agreed under Financing Agreement No PG/FED/21643 is as follows:

| HUMAN RESOURCE DEVELOPMENT PROGRAMME PHASE 1 - BUDGET OVERVIEW |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Components | EUR | PGK | Result-Area (RA) | % | Contracting Authority |
| 1. Capacity building for education sector management | 2,208,000.00 | 6,094,080.00 | RA1 | 17 | DOE |
| 2. Studies and research (through grants) | 500,000.00 | 1,380,000.00 | RA1 | 3.8 | DOE & DNPM |
| 3. Infrastructure | 5,000,000.00 | 13,800,000.00 | RA3 | 38.5 | DNPM |
| 4. Skills training for tutors and teacher training (scholarships) | 1,638,750.00 | 4,522,950.00 | RA2 & RA3 | 12.6 | DOE |
| 5. Project Management and coordination including TA | 2,160,000.00 | 5,961,600.00 | - | 16.6 | DNPM |
| Visibility | 40,275.00 | 111,159.00 | All | 0.4 | DOE |
| Evaluation and Audit | 302,300.00 | 834,348.00 | - | 2.3 | DNPM |
| Contingencies | 1,150,675.00 | 3,175,863.00 | - | 8.9 | DNPM |
| TOTAL | 13,000,000.00 | 35,880,000.00 | - | 100 |  |
| Exchange Rate | 2.76 | (March 2012) |  |  |  |

The Financing Agreement provides a five-component budget against a three result-area technical provision. The above table shows the five-component budget in relation to the stated support to each of the Result Areas in both EURO and PGK. Component 4 provides some confusion as it supports activities in both Result-Area 2 and 3. As described in 2.4.2 Result-Area 2 above, given the support to Scholarships, there is a relatively small budgetary provision for pre- and in-service Teacher Training and subsequently, the need for prioritisation by the beneficiary in determining how best to apply HRDP1 to this area.

The budget is presented by Result-Area, Activity and Sub-Activity in Chapter 3 below.

## Programme Partnership

HRDP1 is a Sector Policy Support Programme (SPSP). An SPSP is a framework for European Union support by which EU funds contribute to the broadening of ownership of partner countries and increase the alignment of donor funding to national policy and plans; increase the coherence between sectoral policy, spending and results through greater transparency, wider dialogue and a comprehensive view of the sector; and minimise as far as possible the transaction costs associated with the provision of external financing.

The main characteristics of an SPSP - An SPSP contributes to the funding of the sector programme, and consequently shares its objectives. No activities outside of the sector programme may be financed through an SPSP - The financial contribution made through an SPSP should be included within the envelope of available financing with a medium-term perspective for the sector. - The monitoring system for the SPSP should be the same as that for the sector programme as a whole. - An SPSP should add value to a sector programme by supporting its objective and its reform-agenda. As such it should be a flexible instrument, which can accompany processes. EuropeAid, July 2007 - Guidelines & Tools Service, Guidelines No 2, Support to Sector Programs

As such the programme must be clearly owned by the GoPNG  - represented by the National Authorizing Officer (NAO) - and implemented by the beneficiary agency, on behalf of the Sector – Department of Education (DOE). These two institutions are critical to the successful implementation of HRDP1 and the Long-Term Technical Assistance (LTTA) must work closely to support their respective leadership and management and the successful implementation of the programme.

Within the DOE, HRDP1 cuts across several divisions (in no order):

- Teacher Education

- Standards and Guidance

- Curriculum Development and Appraisal

- Policy, Planning, Research and Communication

And must work with a number of other departmental divisions in support of service delivery:

- Finance and Administration

- Procurement

- Human Resource and Organization Development

The nature of the SPSP demands departmental mandates and functions are maintained for programme implementation wherever possible. As such, the LTTA will work closely with the above responsible divisions and officers to align the programme.

Across government, HRDP1 aims to strengthen the dialogue function between education and teacher services, finance, treasury, planning, public services, provincial and local level government and so forth. As such, and where possible, the LTTA will work closely with other departments, commissions, agencies and sub-national offices.

The Education Sector of PNG has multiple stakeholders, including Church Agencies and Non-Government Organisations (international and national). These agencies and NGO play critical roles in education institution infrastructure, sector administration and overall education provision. There already exists an extensive framework for inclusion of these actors in the national dialogue. The LTTA will further support the existing structures and where possible support any reformation of the dialogue structures under ESIP.

There is a number of Development Partners (DP) providing support to the Education Sector. AusAID is the largest of the DP and provides support through Technical Assistance and budgetary assistance. AusAID targets the same areas as HRDP1 and at the time of writing provides long-term technical advisors for Planning and EMIS. A Budget Advisor and a Public Financial Management Advisor are forecast for mobilisation in Quarter 4 of 2012. The World Bank provides support to distance education and early childhood development. JICA provides support to distance education. New Zealand Aid provides a grant to the Technical Working Groups for operations and studies.

HRDP1 activities have been assessed against the available plans of DOE and DP. All activities are aligned with the DOE plan and aim to provide added value to on-going initiatives, for example HRDP1 support to M&E will further support DOE EMIS and Census activities, supported by AusAID; and where forecast support is agreed but work plans are not in place, HRDP1 will work closely with incoming advisors to ensure DOE goals are met.

# Plan of Operations

## Inception Findings and Overall work plan for the programme

The overall work plan for the programme remains aligned to our strategy for project implementation, which is explained in our Technical Proposal.  There exist some modifications to the sub-activities of activities as stated in Annex II to the Financing Agreement (N° 21643) and the Logical Framework. Furthermore, there exist some anomalies in the Logical Framework requiring redress at this inception phase, with implication for programme planning and implementation.

The following sections to this chapter provide our comments and recommendations for modification to the Logical Framework and our proposed Action Plan, based upon our more detailed review during the inception phase. An overall programme work plan is appended as Annex III.

### Logical Framework

The Logical Framework or “Logframe” is appended to this Inception Report as Annex V, with the below modifications provided.

PURPOSE

The stated purpose of HRDP1 is: (i) support to UBE and (ii) strengthen SWAp. The Objectively Verifiable Indicators (OVI) include IP7. Percentage of Funds committed with the ESIP increased by x% (as an indication that procedures for implementing projects have been harmonised). The “Important Assumptions” underpinning this indicator are (i) UBE Plan fully financed, and (ii) ESIP fully operationalized. Neither assumption holds true. ESIP in practice exists as the name of the AusAID financed Trust Fund that provides resource for the AusAID Capacity Development Facility (CDF). ESIP as a reform programme was not recognised as a currently running programme by the majority of DOE officers interviewed. UBE operates with a budgetary deficit an annual basis (2011 and 2012). ESIP does not represent what the authors of the HRDP1 Action Fiche believed would culminate from the positive progress in 2009-2010 of the ESIP in support of UBE. Although HRDP1 will support DOE to fully operationalize the ESIP, Indicator IP7 should be removed from the Logframe.

RESULT-AREA 1

Result-Area 1 includes the following OVI. The right-hand column provides recommendations/modifications to the OVI.

| IR1.1 | At least 80% of financial reports submitted by provincial education and district education advisors are provided on time and in line with ruling requirements | No recommendations |
| --- | --- | --- |
| IR1.2 | Production of annual action plans and budgets in line with education plans (national, provincial and district) | No recommendations |
| IR1.3 | At least one Joint Sector Review conducted yearly as from 2011 | At least one Joint Sector Review conducted yearly as from 2013 |
| IR1.4 | EMIS data covering all indicators outlined in the UBE Plan (except financial, administrative and textbook indicators) available as from 2011 | EMIS is supported by AusAID and is not included within the proposed HRDP1 work plan Recommend to remove from OVI |
| IR1.5 | Financial, administrative and textbook indicators included in EMIS by 2013 | Financial, administrative and textbook indicators included in EMIS by 2015 |
| IR1.6 | Percentage of PEA, DEO and inspectors having received management training reaching 100% by 2013, with an increased female proportion of at least 30% | Percentage of PEA, DEO and inspectors having received management training reaching 100% by 2015 The gender reference relates to the recruitment strategy of the DOE and PEA, which is not supported by HRDP1. Recommend to remove from OVI |
| IR1.7 | Percentage of the schools implementing their activities according to approved School Learning Improvement Plan (SLIP) increased by 10% by 2013 | HRDP1 does not directly provide support to SLIP and therefore IR1.7 should not be included in the OVI |
| IR1.8 | Percentage of the District Education Administrators provide quality support to the schools and report back into the system increased by 10% by 2013 | Percentage of the District Education Administrators provide quality support to the schools and report back into the system increased by 10% by 2015 What is the baseline value? |
| IR1.9 | Percentage of the Standard Officers (school inspectors) monitoring and reporting as per agreed upon standards increased by 10% by 2013 | Percentage of the Standard Officers (school inspectors) monitoring and reporting as per agreed upon standards increased by 10% by 2015 What is the baseline value? |
| IR1.10 | Percentage of cadres at National, Regional and Provincial levels meeting the established standards regarding planning, M+E and reporting increased by 10% by 2013 | Percentage of cadres at National, Regional and Provincial levels meeting the established standards regarding planning, M+E and reporting increased by 10% by 2015 What is the baseline value? |
| IR1.11 | At least 4 research studies launched by local research institutions (universities) in collaboration with the Top Management Team | At least 2 research studies launched by local research institutions (universities) in collaboration with the Top Management Team |
| IR1.12 | At least twice a year, there are inter-departmental meetings involving DoE, TSC and related Ministries and departments (especially DNPM, Finance, Treasury, Community Development, Provincial and Local Level Government Affairs [DPLLGA]) and development partners (DP) | No Recommendations |

There exists no baseline to the above indicators in the Financing Conditions. As such, and where available, the 2011 EMIS value will be utilised as the baseline.

RESULT-AREA 2

Result-Area 2 includes the following OVI, with the right-hand column making recommendations/modifications:

| IR2.1 | By 2013, at least 90% of college tutors teach skills and knowledge related to pedagogy and the requirements of OBE, both in In-Service and Pre-Service Training Programmes | By 2015, at least 90% of college tutors teach skills and knowledge related to subject-matter and pedagogy both in In-Service and Pre-Service Training Programmes |
| --- | --- | --- |
| IR2.2 | By 2013, at least 80% of teachers use in their teaching newly obtained skills and knowledge related to pedagogy and the requirements of OBE, as acquired through In-Service and/or Pre-Service Training Programmes | IR2.2 expects approximately 38,000 teachers (80%) to have received training. This is ambitious considering the budget of HRDP1 and limited in-service training provision since 2010. Although this is an admirable goal, it is recommended for this indicator to be removed as unachievable at cessation of HRDP1 |
| IR2.3 | Percentage of qualified teachers increased by at least 5% in 2013 | Percentage of qualified teachers increased by 0.5% in 2014 HRDP1 is training 250 pre-service teachers (approx. 0.5 per cent increase on the 46,000 teachers in PNG). |
| IR2.4 | Percentage of primary school teachers graduating with management training increased by at least 5% in 2013 | OVI not relevant to HRDP1 Given the budget limitation, HRDP1 does not provide in-service training of teachers and uses existing Education Diploma curriculum for Pre-service training (Scholarships), which does not include improved management training content. |

As above, the baseline will be taken from the 2011 EMIS data.

The assumptions under-pinning Result-Area 2 are problematic:

- TTC are firmly committed to decentralized training approaches - suggesting a lack of understanding regarding the funding shortfalls of Teacher Training Colleges (TTC), and

- DOE clearly defines OBE and its related requirements – GoPNG is currently reviewing the Outcome-Based Education (OBE) approach and it is expected that this will result in a movement away from OBE

Support to the TTC Lecturers is identified as a critical factor for strengthening pre- and in-service training, with a focus on subject-content and pedagogy.

RESULT-AREA 3

Result-Area 3 includes the following OVI, with the right-hand column making recommendations/modifications:

| IR3.1 | 100% of student teachers sponsored by scholarships accommodated in expanded capacities at TTC (staff houses, dormitories and classrooms) by 2013 | 100% of student teachers sponsored by scholarships accommodated in expanded capacities at TTC (staff houses, dormitories and classrooms) by 2015 |
| --- | --- | --- |
| IR3.2 | At least 500 primary school teachers coming from remote and underserviced areas trained, 50% of which will be female | At least 250 primary school teachers coming from remote and underserviced areas trained, 50% of which will be female |
| IR3.3 | Teacher absenteeism reduced by at least 2% per year as from 2011 | It is uncertain how IR3.3 fits with the overall HRDP1. |

For further discussion regarding the OVI, see Section 5.1, Definition of Indicators.

The following sections provide our understanding, approach and timeline by Result-Area for implementation given the Financing Agreement, Technical Proposal and Inception Phase

### Result-Area 1: Management capacity of PNG education system strengthened for decision-making, planning, assessment, monitoring

Result-Area 1 supports critical areas of sector management, in-line with our determination of the more critical requirements for a sector-wide approach –medium-term planning and budgeting, sector monitoring and evaluation, public financial management, procurement and overall communication, including inter-actor dialogue and system reporting – and the legal framework within which all of the above takes place.

The initial activity under Result-Area 1 is a review of where the PNG Education Sector is in regards to the past five-years of initiatives to achieve the SWAp, incorporating the above areas. Based upon the review results and the associated recommendations, the DOE with support from HRDP1 LTTA will develop the required frameworks for implementation. For the most part, this will not require starting from nothing given many documents exist in draft format, for example, the ESIP Manual and the Monitoring and Evaluation (M&E) framework and policy, or already exist but are not being fully utilised, for example the Medium Term Expenditure Framework (MTEF). The core activity here is pulling together the many strands, reviewing, strengthening and aligning them to make a cohesive whole.

Upon arriving at a cohesive whole, sensitization and training materials will be developed to build the capacity of the system and its officer/functionaries at all levels (National, Provincial, District and School Level (Head Teachers)). Where possible, HRDP1 activities will be aligned to current and planned initiatives and existing implementation modes of the DOE. HRDP1 will also strive to provide added value to existing modes of delivery by reviewing practices and making recommendations to strengthen.

HRDP1 will ensure that existing studies, research and programmes are respected wherever possible, to avoid duplicating work and wasting scarce resource. Two notable studies of recent times include the draft Capacity Needs Analysis Report and the associated Capacity Development Plan (Divine World & VSO, 2012) and the Joint Institutional Assessment of the Department of Education (Ernst & Young, 2011). HRDP1 activities will be in alignment with the finalised DOE capacity development plan and, for example, agreed Public Financial Management strengthening activities.

For Result-Area 1, three non-key experts will be recruited utilising the 500 person-day provision within the Eurecna Service Contract: (i) Non-Key Expert 1 - Finance, Procurement and Budgeting Expert; (ii) Non-Key Expert 2 – Monitoring & Evaluation Expert; and (iii) Non-Key Expert 3 – Legal Framework Expert.

The following provides an overview of each of the activities under Result-Area 1.

| 1.1. | STRENGTHEN INTER-MINISTERIAL AND INTER-DEPARTMENTAL DIALOGUE FOR FULLY UTILISING SWAP STRUCTURES ACCORDING TO ESIP, INCLUDING NSA |  |
| --- | --- | --- |
| Description |  |  |
| In 2007, the GoPNG led by the Department of Education launched the Education Sector Improvement Programme (ESIP), otherwise known as the PNG Sector Wide Approach (SWAp). The vision for the Sector under ESIP was: (i) All significant public funding for the sector supports the Education Plan and expenditure programme, (ii) GoPNG leadership of the education development programme; (iii) common approaches adopted across the sector by all funding parties, and (iv) progress towards relying upon Government procedures to disburse and account for public expenditure, however funded. An ESIP Steering Committee was formed in 2009 as were five Technical Working Groups (TWG) co-chaired by DOE and Development Partner (DP) representatives, tasked with putting in place a framework to drive the Education Sector and its actors towards a SWAp. Results have been inconsistent, with draft outputs from the TWG taking in excess of a year to formalise, and possible lack of DOE ownership as DP are required to push for meetings and thus gradually become the driving force. To revitalise the process, the DOE intends to use HRDP1 to review the ESIP process to date, including drafted manuals, Terms of Reference and impact of the ESIP process at National and Sub-National levels. From the results of the review, DOE will utilise HRDP1 to further develop and strengthen the institutional structures and processes horizontally and vertically and build capacity of education officers at all levels to achieve common sector planning, budgeting, monitoring and evaluation. HRDP1 will align activities with that of the Institutional Framework Technical Working Group, notably relating to the anticipated Joint Commitment of Principles and Actions between the Government of Papua New Guinea and Its Partners in the National Education System. |  |  |
| Activity 1.1.1 |  | Review of ESIP at National and Sub-National levels to understand the progress of the PNG SWAp |
| Activity 1.1.2 |  | Support to strengthen the institutional arrangements and procedures in pursuit of the ESIP goals |
| Activity 1.1.3 |  | Support for the review and development of the Education Act 1983 (Consolidated to No. 13 of 1995) |
| Activity 1.1.4 |  | Support for strengthening of medium-term expenditure and annual budgeting against sector plans |
| Outputs |  | ESIP Progress Report, including recommendations for strengthened Leadership, Dialogue, Communication, Reporting, Funding, Budgeting and Expenditure |
|  |  | ESIP Manual incorporating on-going Institutional Framework development |
|  |  | Revision of the Education Act, within the context of the Organic Law and SWAp |
|  |  | Improved DOE and Provincial Education Authority (PEA) sector leadership and dialogue |
|  |  | Strengthened Medium-Term Expenditure Framework applied to medium-term and annual planning and budgeting |
| Inputs |  | Department of Education Division of Policy, Planning, Research and Communication Division of Finance and Administration |
|  |  | HRDP1 Key Expert 1, Team Leader – Carlton Aslett |
|  |  | HRDP1 Non-Key Expert 1, Finance and Budgeting Advisor – tbd |
|  |  | HRDP1 Non-Key Expert 3, Legal Framework Advisor - tbd |
|  |  | PNG Research/Academic Institute, Education Act |
| Risks |  | - The perceived stagnation of ESIP as a vehicle for SWAp results in limited/no GoPNG ownership/interest in SWAp - Horizontal dialogue between education sector and other sectors (e.g. Planning, Finance, Treasury) cannot facilitate actual medium-term planning and budgeting - Vertical dialogue within the education sector and across sub-national sectors is blocked by the existing legal framework - DOE does not fill vacant positions within respective divisions and shortages result in insufficient staff for implementation |
| Assumptions |  | - DOE interest for SWAp - Development Partner interest for SWAp - Sub-national intent to strengthen education sector management and work closely with national levels, and vice versa |
| Indicators of achievement |  | - Education Sector periodic meetings attended by a majority of stakeholders - ESIP Manual endorsed by TMT and NEB - Annual Education Sector Review - Amended Education Act - Sector Communication Strategy - Sector Medium-Term Expenditure Framework (MTEF) linked to DOF medium-term revenue forecasts - Annual Operation and Financial Plans linked to the MTEF |

| Activity 1.1. |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Review of ESIP at National and Sub-National levels to understand the progress of the PNG SWAp |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Support to strengthen the institutional arrangements and procedures in pursuit of the ESIP goals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Support for the review and development of the Education Act 1983 (Consolidated to No. 13 of 1995) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Support for strengthening of medium-term expenditure and annual budgeting against sector plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 1.2. | STRENGTHEN PERFORMANCE M&E SYSTEM AT ALL LEVELS |  |
| --- | --- | --- |
| Description |  |  |
| The Education Sector does not have a formal monitoring and evaluation (M&E) framework, but instead relies upon historic processes at each level and/or more recently introduced initiatives that do not connect as a whole. The result is different levels of the system using different approaches, techniques and schedules resulting in difficult to compare and validate data and difficulties in determining lessons learnt. In 2009-10, DOE set up a Monitoring and Evaluation and Research Committee and developed a draft, incomplete Monitoring & Evaluation Framework, Policy and Manual. HRDP1 will provide support to this committee and DOE officers to finalise the draft, test the framework and implement a sector approach to M&E. This activity is linked to ESIP and will include the commencement of Annual Education Sector Review (AESR) (technical and financial support). HRDP1 will align activities with that of the Performance Appraisal Framework (PAF) Technical Working Group, within the TWG mandate. |  |  |
| Activity 1 |  | Review of Monitoring and Evaluation structures at National and Sub-National levels |
| Activity 2 |  | Strengthen Education Sector M&E System |
| Activity 3 |  | Annual Education Sector Review (AESR) |
| Outputs |  | M&E Framework and Policy |
|  |  | M&E Sector Manual & Training Materials |
|  |  | Education indicators, schedule and reporting by level of operations (M&E Toolkit) |
|  |  | Annual Education Sector Reviews (2013 – 15) |
| Inputs |  | Department of Education Division of Policy, Planning, Research and Communication Division of Finance and Administration |
|  |  | HRDP1 Key Expert 2, Training Advisor - tbd |
|  |  | HRDP1 Non-Key Expert 2, Monitoring & Evaluation Expert – tbd |
| Risks |  | - Horizontal dialogue between education sector and other sectors (e.g. Planning, Treasury, Community Development) cannot facilitate oversight of sector - Vertical agreement within the education sector cannot be reached - DOE does not fill vacant positions within respective divisions and shortages result in insufficient staff for implementation |
| Assumptions |  | - DOE will provide leadership to achieve sector M&E - Sub-national intent to strengthen monitoring and evaluation and work closely with national levels, and vice versa |
| Indicators of achievement |  | - Report making assessment of current M&E practices and capacity levels for M&E - M&E Framework and Policy - M&E Manual and Training Materials - Number of education officers trained during HRDP1 implementation - Annual Education Sector Reviews - Number of compliant school, district and provincial reports delivered on time |

| Activity 1.2 |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Review of Monitoring and Evaluation structures at National and Sub-National levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Strengthen Education Sector M&E System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Annual Education Sector Review (AESR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 1.3. | STRENGTHEN THE MANAGEMENT CAPACITIES OF EDUCATION ADMINISTRATORS AT SUB-NATIONAL LEVELS |  |
| --- | --- | --- |
| Description |  |  |
| The scope of Activity 1.3 is vast and the DOE had chosen to concentrate on the key area specified in the Financing Agreement and Technical Proposal – Public Financial Management & Procurement. Based upon the findings of Ernst & Young (2011), and Assessment of The Procurement Capability and Capacity of the Department of Education, Papua New Guinea (Charles Kendall & Associates, 2010) and in-line with the DOE Capacity Development Plan, HRDP1 will review sector sub-national PFM and procurement practises and existing manuals (where available) within the context of GoPNG laws and requirements. The focus of this activity is to develop user-friendly templates, manuals/self-reference materials and training materials for provincial, district and school level financial management and procurement; and to put in place a financial monitoring mechanism that provides simple control functions at each level of operations. The output of this activity will feed into the Leadership and Management Competency Framework under development by the Division of Standards and Guidance, the associated training materials and its piloting. |  |  |
| Activity 1 |  | Review of the Public Financial Management and Procurement practises at Sub-National levels (Province, district and school) |
| Activity 2 |  | Strengthen system capacity for sector public financial management and procurement |
| Activity 3 |  | Support to Leadership and Management Competency Framework at school level |
| Outputs |  | Education Sector Financial Manual and Procurement Manual |
|  |  | Training Materials for Financial Manual and Procurement Manual |
| Inputs |  | Department of Education Division of Finance and Administration Division of Teacher Education Division of Standards and Guidance Division of Procurement |
|  |  | HRDP1 Key Expert 1, Team Leader – Carlton Aslett |
|  |  | HRDP1 Non-Key Expert 1, Finance and Budgeting Advisor – tbd |
| Risks |  | - PFM and procurement strengthening is not a priority for Sub-national levels - DOE does not fill vacant positions within respective divisions and shortages result in insufficient staff for implementation - Division of Procurement does not become fully operational |
| Assumptions |  | - DOE will provide PFM and Procurement leadership - Sub-national intent to strengthen PFM and Procurement and work closely with national levels, and vice versa |
| Indicators of achievement |  | - Report providing status of PFM and Procurement practises at sub-national level and recommendations for system and functionary capacity strengthening - PFM Manual - Procurement Manual - Training Manuals - Number of education officers trained during HRDP1 implementation - Number of Head Teachers trained during HRDP1 implementation |

| Activity 1.3 |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Review of the Public Financial Management and Procurement practises at Sub-National levels (Province, district and school) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Strengthen system capacity for sector public financial management and procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Support to Leadership and Management Competency Framework at school level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 1.4. | STRENGTHEN INVOLVEMENT OF PAPUA NEW GUINEA RESEARCH AND ACADEMIC INSTITUTIONS IN MANAGEMENT TRAINING |  |  |
| --- | --- | --- | --- |
| Description |  |  |  |
| Activity 1.4 includes the human resource capacity building interventions related to Activities 1.1 through 1.3. The focus of the capacity building is provincial and district officers and head teachers. Where possible, tertiary institutions and/or research institutions will be invited to participate in the development of materials and delivery of training. However, given the limited budget, high training costs of Papua New Guinea, focus of training at sub-national levels and limited out-reach capacity of tertiary institutes, a within system solution for training is required. This is in-line with the DOE In-service plans for sector capacity building and HRDP1 will support the National In-Service Committee (NIC), mandated as responsible for teacher and head teacher training. The PNG Education Institute (PNGEI) is specifically identified in the Action Fiche and included in our proposal. It is unknown as to the detailed capacity of the institute and this will require further exploration during implementation. The assumption, and a clear reason why PNGEI was identified as a possible agent for decentralised training, that PNGEI has satellite campuses across the regions and/or provinces appears false. At provincial and district levels, all officers will receive training in the areas of sector coordination, dialogue, M&E, medium-term budgetary planning, PFM and procurement. At school level, HRDP1 will support DOE in developing Head teacher training structures, including the use of clusters and senior trainers from high schools and standards officers as trainers. To date there exists approximately 12,500 Head teachers across all types of schools in PNG. It is impossible to provide training to all Head teachers under the HRDP1 budget. However, the HRDP1 budgetary commitment to Head Teacher training will be utilised by DOE as a catalyst for securing additional funding to expand the finalised training programme. Subject to the finalised DOE model for delivery, the number of Head Teacher to be trained under the HRDP1 budget will be agreed. |  |  |  |
| Activity 1 |  | Provincial, District and De-concentrated Officer Capacity Building |  |
| Activity 2 |  | School Level Capacity Building |  |
| Activity 3 |  | Involve PNG research and academies in studies on education |  |
| Outputs |  | Report outlining Training Model for all sub-national personnel |  |
|  |  | National Training for Province and District Officers (2 times during HRDP1) |  |
|  |  | Head Teacher Training as part of Leadership and Management Competency Framework Training |  |
| Inputs |  |  | Department of Education Division of Policy, Planning, Research & Communication Division of Finance and Administration Division of Teacher Education Division of Standards and Guidance Division of Procurement |
|  |  |  | PNG Research/Tertiary Institute - tbd |
|  |  |  | HRDP1 Key Expert 1, Team Leader – Carlton Aslett |
|  |  |  | HRDP1 Key Expert 2, Training Advisor |
|  |  |  | HRDP1 Non-Key Expert 1, Finance and Budgeting Advisor – tbd |
|  |  |  | HRDP1, Non-Key Expert 2, Monitoring & Evaluation Expert - tbd |
|  |  |  | Grant – Education or Research Institute |
| Risks |  | - Sub-national officer and head teacher in-service training congestion during summer vacation - Training costs increase substantially reducing scope of training - DOE does not fill vacant positions within respective divisions and shortages result in insufficient staff for implementation - Division of Procurement does not become operational |  |
| Assumptions |  | - Sub-national intent to strengthen education sector management and work closely with national levels, and vice versa - DOE endorsement of the Leadership and Management Competency Framework |  |
| Indicators of achievement |  | - Number of education officers trained during HRDP1 implementation - Number of Head Teachers trained during HRDP1 implementation |  |

| Activity 1.4 |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Provincial, District and De-concentrated Officer Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | School Level Capacity Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Involve PNG research and academies in studies on education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

### Result-Area 2 - Pedagogical and management skills of basic education school teachers improved

Result-Area 2 has been reduced given the budget limitations and existing Programme Estimate commitment to Scholarships (see 3.1.4 Result-Area 3, below). Through dialogue with DOE Division of Teacher Education, and given the available budget, it is recommended that the core focus of support is to strengthen the knowledge and capacity of Teacher Training College (TTC) Lecturers. In particular, a consensus of DOE officers has pointed to concern relating to subject-matter knowledge and pedagogy skills of Lecturers, impacting the quality of pre-service entrants to the teaching profession.

There exists a Master’s programme within the PNG Tertiary System for Education Leadership (and Management), which TTC Leaders and Lecturers are beginning to benefit from. Given this existing provision, it is not recommended that HRDP1 supports the development of management skills.

TTC Lecturers in previous years were the beneficiary of an annual, certified in-service training entitled the “Associate Lecturer Programme”. The programme, led by DOE, had its curriculum developed by the TTC through “Inter-College Subject Committees”. This allowed for greater ownership of the development process by the beneficiaries of the programme and therefore a more tailored subject matter resulting in needs being met. This programme has lapsed in recent years and no support for the professional development of TTC Lecturers currently exists.

There are 14 Teacher Training Colleges in Papua New Guinea, of which 10 are members of the Teacher Service Commission (TSC) and 4, the Public Service Commission (PSC). The exact number of lecturers is unknown but estimated around 280 persons. This data is in the process of being collected. The majority of TTC are church-agency managed and dialogue will be required to determine if any counterpart funding will come from the HRDP1 provision.

| PNG Teacher Training Colleges (and Agency Ownership) |  |
| --- | --- |
| Balob TC, Morobe (Lutheran/Anglican) | OLSH TC – Kabaleo, ENB (Catholic) |
| Dauli TC, Southern Highlands (Evangelical Alliance) | PNGEI, NCD (Government) |
| Enga TC, Enga (Lutheran) | Sacred Hearts TC, NCD (Catholic) |
| Gaulim TC, ENB (United Church of PNG) | Sonoma Adventist TC, ENB (Seventh Day Adventist SDA) |
| Holy Trinity TC, WHP (Catholic) | Divine World University, East Sepik (Catholic) |
| Madang TC, Madang (Government) | Pacific Adventist University, NCD (SDA) |
| Melanesia Nazarene TC, WEP (Nazarene) | University of Goroka, EHP (Government) |

The DOE has requested support to resurrect the Associate Lecturer Programme. Activity 2.1 will provide this support.

| 2.1. | CARRY OUT IMMEDIATE SKILLS TRAINING FOR TTC LECTURERS WITH A PRIME FOCUS ON PEDAGOGY AND MANAGEMENT |  |
| --- | --- | --- |
| Description |  |  |
| Activity 2.1 will provide technical and financial support for the development of a TTC Lecturer competency framework, TTC sample needs analysis and in-college in-service trainers, development of modular programme, testing materials, production of materials, training of trainers and training of lecturers over a two-year period. Focus will be paid to what already exists, what previously has worked well and modernising this within the context of Papua New Guinea. Review, analysis and programme development will look to include TTC representatives, including the reintroduction of Inter-College Subject Committees. Delivery methods to Trainers and Lecturers will be developed with the TTC with the focus on cost-efficiency and thus, increased sustainability. |  |  |
| Activity 1 |  | Needs Analysis of Teacher Training Colleges (TTC) and TTC Lecturers |
| Activity 2 |  | Produce In-Service Training Programme for TTC Lecturers |
| Activity 3 |  | Conduct Training of Trainers of Lecturers (n=42) |
| Activity 4 |  | Conduct In-Service Training for TTC Lecturers |
| Activity 5 |  | Conduct Impact Assessment mid-year after training (Year 1 and Year 2) |
| Outputs |  | TTC Lecturer Competency Framework |
|  |  | Training Needs Analysis |
|  |  | Programme Materials |
|  |  | Certification of Programme Materials |
|  |  | Two-Year Training and Impact Monitoring Schedule |
|  |  | Training of 42 Trainers of Lecturers (three per TTC) |
|  |  | Training of 280 Lecturers (approx) – Year 1 and Year 2 |
|  |  | Impact Assessment Report & Recommendations |
| Inputs |  | Department of Education Division of Teacher Education Division of Standards and Guidance |
|  |  | Grant – PNG Education Institute |
|  |  | HRDP1 Key Expert 2, Training Advisor |
| Risks |  | - DOE does not fill vacant positions within respective divisions and shortages result in insufficient staff for implementation - TTC do not have sufficient capacity to release three lecturers during the academic year in order to carry out Training-of-Trainer training |
| Assumptions |  | - TTC embrace the development/reintroduction of certified in-service training - TTC embrace the reintroduction of inter-College Subject Committees - DOE approves certification of final programme materials |
| Indicators of achievement |  | - TTC Lecturer Competency Framework & Programme Materials - Training of 42 Trainers of Lecturers (three per TTC) - Training of 100% of TTC Lecturers - Impact Assessment Report |

| Activity 2.1 |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Needs Analysis of Teacher Training Colleges (TTC) and TTC Lecturers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Produce In-Service Training Programme for TTC Lecturers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Conduct Training of Trainers of Lecturers (n=42) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Conduct In-Service Training for TTC Lecturers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Conduct Impact Assessment mid-year after training (Year 1 and Year 2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

### Result-Area 3: Access of teachers to pre-service and in-service training improved

Result-Area 3 looks to address some of the demand for teachers in more rural, educationally under-serviced communities by increasing the supply of places and dormitories at TTC (infrastructure support) and providing resource (scholarships) for individuals from such-communities to achieve their Education Diploma and return to their community school to teach. Both programmes commenced prior to the arrival of the LTTA.

The infrastructure programme, like the other HRDP1 activities, has a limited budget (EUR 5 million). With the relatively high cost of works materials and labour and diminishing value of the Euro, the 2010 budget estimates have even less value at 2012 prices. The program status at the time of writing is behind schedule. A scoping exercise to determine where and what the investment should target has resulted in an unsubstantiated plan for support to eight colleges (Framework contract EuropeAid/127054/C/SER/multi). No dialogue has taken place to encourage national, sub-national or church agency counterpart funding, which can be seen as an opportunity lost. As such the programme will likely remain at EUR 5 Million with no additional funds coming from other stakeholders. The current draft plan includes the below, however the final report remains non-approved by the Top Management Team:

| Teacher Training College | N° of Classrooms | N° of Male Dormitories | N° of Female Dormitories | N° of Staff Houses |
| --- | --- | --- | --- | --- |
| PNGEI | 2 | 1 | 1 | 6 |
| BOMANA | 2 | 1 | 1 | 4 |
| BALOB | 2 | 1 | 1 | 4 |
| Mt HAGEN HTTC | 2 | 1 | 1 | 5 |
| NAZARENE | 2 | 1 | 1 | 6 |
| DAULI | 2 | 1 | 1 | 6 |
| GAULIM | 2 | 1 | 1 | 6 |
| MADANG | 2 | 1 | 1 | 6 |

The number of TTC receiving support is expected to be reduced.

It is hoped that initial design and supervision activities will commence in Quarter 4, 2012.

The second activity in support of TTC infrastructure relates to Information Communication Technology (ICT) infrastructure. Given the limited budget for infrastructure and the identified need for physical infrastructure expansion, HRDP1 will not support ICT infrastructure expansion.  DOE is looking to other DP for support in the development of TTC ICT infrastructure from 2013 onwards.

The Scholarship programme provides funds for students from rurul, educationally under-serviced communities to attend a TTC and qualify as a primary school teacher, before returning (in principle) to their community. The number of participating students by year and TTC is as follows:

| Teacher Training College | Year 1 |  | Year 2 |  |
| --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female |
| Bomana (Sacred Heart), NCD | 51 | 49 | 3 | 2 |
| Gaulim, East New Britain | 33 | 27 | 0 | 4 |
| Dauli, Southern Highlands | 59 |  | 22 |  |

Note: Dauli TC Report providing breakdown by gender outstanding at time of writing

| 3.1. | IMPROVE INFRASTRUCTURE IN TEACHER TRAINING COLLEGES |  |
| --- | --- | --- |
| Description |  |  |
| The expansion of existing TTC campuses (through the construction of classrooms, dormitories and lecturer housing) to meet demand for teachers from educationally under-serviced communities. This intervention is a specific commitment, directly contracted by the National Authorising Officer (NAO) through the NAO Support Unit (NAO-SU). |  |  |
| Activity 1 |  | Construct and equip classrooms and other school facilities |
| Activity 2 |  | Provide TTC with the technology to gain access to PNG-ARNet |
| Outputs |  | Finalised Design of infrastructure under the works programme |
|  |  | Construction of classrooms, dormitories and lecturer housing |
| Inputs |  | Department of Education Division of Planning, Policy, Research and Communication |
|  |  | National Authorising Officer Support Unit (NAO-SU) |
|  |  | Service Contractor: Design and Supervision of HRDP1 Works (Specific Commitments) - tbd |
|  |  | KE1 – Team Leader, Carlton Aslett |
|  |  | Works Contractors (Specific Commitments) - tbd |
| Risks |  | - Maximum return on investment is not achieved given no counterpart funding and the current strategy of providing nominal support across the majority of TTC - Inflation continues to increase reducing the scope of the budgetary commitment - PNG contractors struggle with EC PRAG procedures and templates - Poor project and financial management by contractors leads to delays to construction programme |
| Assumptions |  | - Continuous communication between NAO SU and DOE resulting in agreement regarding infrastructure programme - Quality of Design and Supervision contractor is good resulting in strong controls for contractor project and financial management - Local/TTC ownership and oversight to ensure daily monitoring of works’ activities on site |
| Indicators of achievement |  | - DOE endorsed TTC infrastructure drawings - Works’ contracts by TTC - Infrastructure hand-over to TTC |

| Activity 3.1 |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Construct and equip classrooms and other school facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 3.2. | ENHANCE ACCESS FOR IDENTIFIED TRAINEE TEACHERS COMING FROM AND RETURNING TO REMOTE AND UNDERSERVICED COMMUNITIES |  |
| --- | --- | --- |
| Description |  |  |
| Provision of scholarships for 219 (2 years funding) and 31 (1 years funding) students covering tuition, accommodation, wellbeing and travel costs between home and college. |  |  |
| Activity 1 |  | Identify communities where availability of teachers is scarce |
| Activity 2 |  | Provide scholarships for teachers from remote communities |
| Outputs |  | 2012: 31 primary teacher graduates |
|  |  | 2013: 219 primary teacher graduates |
| Inputs |  | Department of Education Division of Teacher Education |
|  |  | KE1, Team Leader – Carlton Aslett |
|  |  | Service delivery by Bomana, Gaulim and Dauli Teacher Training Colleges |
| Risks |  | - Students do not return to their communities upon completion |
| Assumptions |  | - Students with less than Grade 12 qualification have sufficient knowledge and capacity to undertake the Education Diploma, and/or TTC provide sufficient academic support - Teacher Training Colleges will provide suitable level of care to students during their residency |
| Indicators of achievement |  | - TC annual enrolment reports - TC annual mid-tear reports - TC annual final reports |

| Activity 3.2 |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  | 2014 |  |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| 1 | Identify communities where availability of teachers is scarce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Provide scholarships for teachers from remote communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

For a detailed breakdown of the overall HRDP1 programme, including sub-sub activities, please refer to Annex III.

### HRDP1 Indicative Budget

The indicative budget by Result-Area and Activity is as follows:

| ACTIVITY NO. | ACTIVITY DETAILS | Proposed Modifications |
| --- | --- | --- |
| Result-Area 1 | Management capacity of PNG’s education system for decision-making, planning, assessment, monitoring of education system | 8,077,000.00 |
| 1.1 | Strengthen inter-ministerial and inter-departmental dialogue for fully utilising SWAp structures according to ESIP, including NSAs | 1,492,220.00 |
| 1.1.1 | Review of Education Sector Improvement Programme at National and Sub-National levels to understand the progress of the PNG SWAp | 409,380.00 |
| 1.1.2 | Support to strengthen the institutional arrangements in pursuit of the ESIP goals | 117,760.00 |
| 1.1.3 | Support for the development of a Single Education Policy/Review of Education Act and Alignment of Education Policies within Legal Framework | 694,780.00 |
| 1.1.4 | Support for the strengthening of medium-term expenditure and annual budgeting against sector plans | 270,300.00 |
| 1.2 | Strengthen performance M&E system at all levels | 2,409,480.00 |
| 1.2.1 | Review of Monitoring and Evaluation structures at National and Sub-National level | 68,200.00 |
| 1.2.2 | Strengthen Educstion Sector M&E system | 1,076,580.00 |
| 1.2.3 | Annual Education Sector Reviews (AESR) and support to decision-making at all levels | 1,264,700.00 |
| 1.3 | Strengthen the management capacities of education administrators at sub-national levels | 932,920.00 |
| 1.3.1 | Review of Public Financial Management and Procurement practises at Sub-national levels (province, district and schools) | 174,760.00 |
| 1.3.2 | Strengthen system capacity for sector public financial management and procurement | 592,160.00 |
| 1.3.3 | Support to Leadership and Management Competency Framework at school level | 166,000.00 |
| 1.4 | Strengthen capacity of the PNG Education Sector utilising research and academic institutions in management training | 3,242,380.00 |
| 1.4.1 | Provincial, District and Deconcentrated Officer Capacity Building | 1,631,500.00 |
| 1.4.2 | School Level Capacity Building | 1,334,880.00 |
| 1.4.3 | Involve PNG research and academic Institutoins in studies on education | 276,000.00 |
| Result-Area 2 | Pedagogical and management skills of basic education school teachers improved | 2,046,552.00 |
| 2.1 | Carry out immediate skills training for TTC lecturers with a prime focus on pedagogy (OBE requirements, ICT, etc) and management | 2,046,552.00 |
| 2.1.1 | Needs analysis of TTCs and TTC lecturers | 124,720.00 |
| 2.1.2 | Produce in-service training materials for TTC lecturers | 124,320.00 |
| 2.1.3 | Conduct training of 42 Trainers of Trainers (Port Moresby) | 567,000.00 |
| 2.1.4 | Conduct nationwide in-service training for TTC lecturers | 1,108,712.00 |
| 2.1.5 | Conduct impact assessment mid year after training for both Year 1 and Year 2 | 121,800.00 |
| Result-Area 3 | Access of teachers to pre-service and in-service training improved | 17,488,000.00 |
| 3.1 | Access of teachers to pre-service and in-service training improved | 13,800,000.00 |
| 3.1.1 | Construct and equip classrooms and other school facilities | 13,800,000.00 |
| 3.1.2 | Provide TTC with the technology to gain access to PNG-ARNet | - |
| 3.2 | Enhance access for identified trainee teachers coming from and returning to remote and underserviced communities | 3,688,000.00 |
| 3.2.1 | Identify communities where availability of teachers is scarce | - |
| 3.2.2 | Provide scholarships for teachers from remote communities | 3,688,000.00 |
|  | PROGRAMME TOTAL | 27,611,552.00 |

The above budget is indicative, awaiting formalisation by DOE prior to submission to NAO. For a detailed budget overview, the draft Programme Estimate Annex 3 is attached to this report as Annex VII.

## Plan of operations for the next period

For the next reporting period (ending in February 2013) the following activities will be implemented.

### Result-Area 1: Management capacity of PNG education system strengthened for decision-making, planning, assessment, monitoring

| 1.1 STRENGTHEN INTER-MINISTERIAL AND INTER-DEPARTMENTAL DIALOGUE FOR FULLY UTILISING SWAP STRUCTURES ACCORDING TO ESIP, INCLUDING NSA | - Development of Review Methodology - Desk study, interview and workshops at national and sub-national levels - Commencement of committee - Recruitment of Non-Key Expert 3 |
| --- | --- |
| 1.2 STRENGTHEN PERFORMANCE M&E SYSTEM AT ALL LEVELS | - Recruitment of Non-Key Expert 2 - Development of Review Methodology - Desk study, interview and workshops at national and sub-national levels |
| 1.3 STRENGTHEN THE MANAGEMENT CAPACITIES OF EDUCATION ADMINISTRATORS AT SUB-NATIONAL LEVELS | - Recruitment of Non-Key Expert 1 - Development of Review Methodology - Training Need Analysis - Commencement of committee |
| 1.4 STRENGTHEN INVOLVEMENT OF PAPUA NEW GUINEA RESEARCH AND ACADEMIC INSTITUTIONS IN MANAGEMENT TRAINING | - No activity |

### Result-Area 2: Pedagogical and management skills of basic education school teachers improved

| 2.1 CARRY OUT IMMEDIATE SKILLS TRAINING FOR TTC LECTURERS WITH A PRIME FOCUS ON PEDAGOGY AND MANAGEMENT | - Completion of recruitment of replacement KE2 - Development of TTC Assessment methodology and tools - Development of TTC Lecturer Competency Framework - Commencement of Training Needs Analysis |
| --- | --- |

### Result-Area 3: Access of teachers to pre-service and in-service training improved

| 3.1 IMPROVE INFRASTRUCTURE IN TEACHER TRAINING COLLEGES | - Finalise scope of infrastructure and budget for works, supervision, ICT and goods and chattels - Contract Service provider for Design and Supervision - Commence contracting for Works Contracts |
| --- | --- |
| 3.2 ENHANCE ACCESS FOR IDENTIFIED TRAINEE TEACHERS COMING FROM AND RETURNING TO REMOTE AND UNDERSERVICED COMMUNITIES | - Finalise Scholarship Agreements and initial payments to students - Develop monitoring tools for college and external monitoring - Complete Year 1 - Return students to home communities - Receive Final Reports for Year 1 |

# Implementation Arrangements

## Project Management

Our approach to HRDP1 will be characterised by strong contract management, including:

- Client liaison with the Department of Education (beneficiary) and National Authorizing Officer (via the NAO SU)

- Constant monitoring of contract activities

- Internal audit of programme accounts

- Quality control of deliverables

- Team management and motivation

- Travel and accommodation

- Mobilisation of experts and their replacement if and when necessary

A full-time backstopping unit at Eurecna headquarters will provide consistent support to the project implementation and to the coordination of consortium inputs. The Contract Manager, Romina Carrer, has been appointed to take care and coordinate all daily issues where the project team may be in need of assistance.

## Logistics

The programme beneficiary has placed at our disposal an office on the 5th Floor within the Department of Education at Fincorp Haus.  Upon arrival of Key Expert 2, a second office within the Division of Teacher Education will also be made available. Offices will be equipped with personal computers and relevant consumables, in-line with DOE ICT policy. Both key experts will be provided with mobile phone cards. The address of the Service Contract office is:

HRDP1 Long-Term Technical Assistance

Att: Carlton Aslett, Team Leader

Department of Education

5th Floor, Fincorp Haus

Independence Drive, WAIGANI

Port Moresby, NCD

Tel: 		+675 7116 1471 / +675 7222 8230

Email 1:	Carlton_Aslett@education.gov.pg

Email 2:	carltonas@gmail.com

## Reporting

The Team Leader will liaise directly with the designated beneficiary Project Manager – Mr. Joe Logha, Assistant Secretary, Planning, Policy, Research and Communication Division and the NAO SU. Regular meetings will be held to report on and review progress. DOE will provide short Quarterly Reports with support from the LTTA. Semi-Annual Reports will also be provided in accordance with the TOR. The Team Leader will be responsible for coordinating and drafting the interim reports. The First Interim report will cover the period from Inception Report to 31st December 2012. In line with the TOR, the draft Final Report will be provided at the latest by 19th September 2015. The Final Report will be then completed by 20th October 2015.

| 2012 |  |  |  |  |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| Inception Period |  |  | 1st Interim Report |  |  |  | 2nd Interim Report |  |  |  |  |  | 3rd Interim Report |  |  |  |  |  |  |

| 2014 |  |  |  |  |  |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 |
| 4th Interim Report |  |  |  |  | 5th Interim Report |  |  |  |  |  | 6th Interim Report |  |  |  |  |  | Final Report |  |  |

## Coordination

As stated in the TOR, a Programme Steering Committee, a Technical Steering Committee and Component Focal Points (within DOE) will be set-up. Terms of Reference for each have been developed and the Beneficiary has nominated functionaries from within the Department of Education and other relevant departments to serve under each.

The institutional basis of HRDP1 is beneficiary ownership. As much as possible, all activities and administration of HRDP1 will be carried out using DOE systems and DOE personnel. The Component Focal Points play a critical role in mainstreaming HRDP1 throughout the DOE. They become the de facto technical managers for each component/result-area overseeing the respective division(s) officers in the execution of tasks to implement activities.

The Technical Steering Committee (renamed as the HRDP1 Technical Focal Group) is a quarterly committee tasked with reviewing progress of implementation and plans for the forthcoming quarter. It is not a committee to “tick” boxes, but rather one to review the technical merits of proposals and progress and support HRDP1 activities that meet obstacles or are lagging in the implementation. The NAO SU has a representative member to this group and the Delegation of the European Union is invited as an observer. The Group will meet on a quarterly basis plus on an extraordinary basis if and when the need arises.

The Secretary of Education, the HRDP1 Supervisor on behalf of the Beneficiary, chairs the Programme Steering Committee. Members of the committee include representation from the departments of Planning and Monitoring, Finance, Treasury and Community Development. This committee is important to the success of the programme and includes the non-education sectors that provide critical inputs for the successful delivery of education. The Committee will meet twice yearly plus on an extraordinary basis if and when the need arises.

HRDP1 Institutional Arrangements

The Secretary of Education has nominated the Assistant Secretary, Policy, Planning, Research and Communication as his designate for day-to-day supervision and management of HRDP1.

## Resources and Budget

### Human resources

The nominees for Team Leader and the Key Expert were approved upon acceptance of the contractor’s technical proposal. Unfortunately, due to the ill-health of the Key Expert 2 (KE2) – Training Advisor between contracting and mobilisation, a replacement KE2 is required. At the time of writing, the Contracting Authority and Service Contractor are moving towards agreement on this issue.

In addition, the LTTA includes 500 person days of non-key experts (NKE), here defined as providing input no longer than 6 consecutive person months. The NKE positions are not finalised during the contracting process as they are designed to support the activities of the result-areas validated/amended during the inception phase.

The scope of HRDP1 is relatively large in relation to the provision for technical assistance and the budget. Eurecna will during the course of implementation, and in collaboration with DOE, discuss with the Contracting Authority the  suitability of short-term input provision against the work plan to determine the need for additional days if required.

The Key Experts at the time of writing are comprised as follows:

| Name of Expert | Team Position |
| --- | --- |
| Carlton Aslett | Key Expert 1, Team Leader |
| To be determined | Key Expert 2, Training Advisor |

The indicative Non-Key Positions are as follows:

| Name of Expert | Team Position |
| --- | --- |
| To be determined | Non Key Expert 1, Public Financial Management and Budgeting Advisor |
| To be determined | Non Key Expert 2, Monitoring & Evaluation Advisor |
| To be determined | Non Key Expert 3, Legal Framework Advisor |

The Terms of Reference for each of the above positions will be developed during the drafting of the Addendum to the Programme Estimate.

### Input Utilisation

No changes are being proposed to the planned man-day allocation set out in the technical proposal as can be seen in the following table:

| Category of Expert | Days Planned | Technical Proposal |
| --- | --- | --- |
| KE1 Team leader, Carlton Aslett | 734 | 734 |
| KE2 Training Advisor, To be determined | 734 | 734 |
| Non-Key Experts, To be determined | 500 | 500 |

The situation in regard to the appropriate use of man-days by expert category will be kept under close review by the Team Leader and any necessary recommendations will be made to the Contracting Authority for changes to enable project activities to be effectively implemented.

Given the ill-health of KE2, a reduced amount of days were input during the inception period. This and the following other factors made the inception period problematic:

- Only one Key Expert was in country

- The inception period took place during a frantic period within the DOE with the Senior Education Officer’s Conference and School Fee Free Subsidy issues among other activities resulting in limited time with DOE officers

- The HRDP1 Programme Estimate (for Scholarships) was running upon the arrival of the LTTA with limited /no set-up for Programme Estimate Administration resulting in the need for LTTA support immediately upon arrival

- The HRDP1 Infrastructure Programme scoping exercise and development of Design and Supervision Terms of Reference (Framework contract) failure to deliver suitably validated outputs of an appropriate quality has resulted in further time away from task for the LTTA

- DOE confusion regarding the outstanding closure issues for EDF9 Programme Estimates (n=2) and the introduction of the new Programme Estimate for EDF10 has further demanded LTTA support

However, the involvement of the LTTA in the above issues has also highlighted key lessons-learnt that will strengthen HRDP1 implementation. Notably, these include:

1. DOE Officers must be fully briefed prior to their taking of decisions. There is evidence that external pressures on DOE to move forward rapidly often results in less than optimum decision-making and planning. A good example is the greater than forecast commitment of funds on scholarships, resulting in a smaller provision for in-service teacher training; and the drafting of budgets for infrastructure (works) support without consideration for other activities (furniture and ICT) within the same budget line.

2. There is limited evidence of EDF procedure capacity in the DOE. Outstanding EDF9 issues have revealed that DOE were mainly recipients of support for their administration duties – e.g. the Imprest Accounting Officers have never been required to formulate Records of Expenditure, only sign them. This lack of empowerment has been one cause for poor closure performance under EDF9.

3. There appears to be little ownership by DOE of the forecast specific commitments (works). It is critical for NAO SU and DOE to further develop their partnership and maintain strong communications during implementation.

During the period from 20th June to 31st August 2012, the following input was made by the LTTA:

| Category of Expert | Person days June / August 2011 |
| --- | --- |
| Team leader, Carlton Aslett | 54 |
| Training Advisor, to be determined | 0 |

### Incidental Expenditure

The Incidental expenditures will be used as stated in the provisions in the General Conditions and the notes in Annex V of the contract. The provision for incidental expenditure for this contract is € 50,000 and will be utilised, as per TOR, to cover:

- Authorized travel and per diems for programme purposes

It is noted that given the need to travel by aircraft for most missions (expected average cost PGK 1,250), the exorbitant cost of accommodation in PNG and the core focus of HRDP1 at sub-national level, the provision for incidental expenditure is insufficient for LTTA implementation during the 40 month implementation period. This will need to be addressed in subsequent dialogue with the Contracting Authority.

## Team Management

The programme activities will be carried out by DOE and other sector officers, with support from each team member of the LTTA (KE and NKE). The LTTA team is co-ordinated by the Team Leader.

The indicative list of required NKE to be engaged during the coming period in relation to the planned activities, is as follows:

| NKE | Position Title | Activity/Sub-Activity |  |  |
| --- | --- | --- | --- | --- |
|  |  | Primary Focus | Secondary Focus | Tertiary Focus |
| NKE1 | Public Financial Management & Budgeting Advisor | 1.3 | 1.1.4 | 1.4 |
| NKE2 | Monitoring & Evaluation Advisor | 1.2 | 1.1.2 | 1.4 |
| NKE3 | Legal Framework Advisor | 1.1.2 |  |  |

Team management is under the responsibility of the Team Leader, the Beneficiary Project Manager and the Contract Manager.

Proper management of the team will be ensured by:

- Constant exchange of information (via ad-hoc meetings, email, Skype and phone);

- Weekly meetings of the long-term team;

- Daily contact with the backstopping unit via our Intellweb IT management system.

## Financial Management

The programme requires the delivery of specialised technical inputs and the mobilisation of substantial financial resources for its operations. The DOE is the responsible institution for Programme Estimate Imprest Account management. The LTTA is responsible to support the administration of the Imprest Team responsible for the Imprest Account. In addition, DOE must adhere to national public financial management procedures as decreed by PNG law.

The LTTA will thus provide support in the setting up imprest management processes, including the development of templates and manuals where necessary, ensuring that additional bureaucracy to current PNG requirements is minimised, while maintaining compliance with EC Practical Guide to Contract Procedures for External Actions (PRAG). The DOE will operate a zero-tolerance policy in relation to acquittals of advances and timely delivery of receipts, boarding passes and so forth. Failure by any individual to comply will result in penalties culminating in an individual no longer participating on HRDP1 implementation.

The LTTA will further provide support in the development of the necessary controls to ensure compliance of execution and reporting. DOE accounting officers will receive training to populate and deliver accurate records of expenditure and replenishment requests in a timely fashion. This is a critical lesson learnt from the EDF9 ETHRDP, whereby DOE personnel were ill-equipped to manage the imprest accounts on the withdrawal of the LTTA.

Financial Management best practice would require the use of a closed accounting system for management of accounts. As a Sector Policy Support Programme, HRDP1 should use the government accounting information system for management of accounts. The LTTA will explore with the Beneficiary and Contracting Authority the possibilities for management of the Imprest Account.

For accounting of Service Contract operational funds (non-reimbursable), a local bank account has been opened and the Team Leader has received full Powers of Attorney from Eurecna.

## Project Visibility

One of the most important elements for education reform and development is to ensure proper visibility of the planned activities and implemented tasks. Within the next Interim Report, the DOE and LTTA will prepare a detailed Visibility Plan, based on the selection of the most relevant information channels to be used in supporting our planned activities.

# Monitoring and Evaluation

The monitoring of the activities to be implemented within this project will be conducted according to general standards and in line with the following specific indicators.

## Definition of indicators

The stated Objectively Verifiable Indicators (OVI) to the “Programme Purpose” in the HRDP1 Log frame Matrix (see annex X) are:

| IP1 | Pupil: Teacher Ratio (PTR) maintained around 34:1 in line with current student intake by 2013 |
| --- | --- |
| IP2 | Net enrolment ratio in primary schools (MDG indicator #6) increased to exceed 59.1% (Female: 58%; Male: 59.9%) by 2013 |
| IP3 | Gender parity index is showing consistent linear progress towards exceeding 0.955 by 2013 |
| IP4 | Transition rate (Grade 8→9) remains stable at 55% with an absolute increase of learners to at least 43,000 by 2013 (2007: 35,676 learners) |
| IP5 | Percentage of Primary School Teachers with at least diploma qualification increased to at least 84.4% (Female: 85.8; Male: 83.2%) by 2013 |
| IP6 | Difference in Prep to Grade 8 NER between highest and lowest districts reduced from 57% in 2010 to less than 46.3% by 2013 |
| IP7 | Percentage of funds committed within the ESIP increased by x% |

The above OVI were based upon the programme commencing in 2010 and the 2013 date should reflect the actual implementation period of this programme, 2012-2015.

These OVI are chosen to represent UBE. If we add indicator values for last collected census (2011), we arrive at the following set of values:

| DAC code | Description | Indicator name | Baseline Value (Formulation) | 2011 EMIS Values | Estimated 2013 value (Formulation) | Estimated 2015 value | Source | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11110 | Education policy and administrative management | Pupil/teacher ratio [2] | 33.4 | 34.77 | 33.7 | tbd | EMIS |  |
| 11120 | Education facilities and training | Percentage of trainers trained | n/a | n/a | n/a | n/a | - | Data not collected by Government |
| 11130 | Teacher training | Percentage of trainers trained | n/a | n/a | n/a | n/a | - |  |
| Basic Education |  |  |  |  |  |  |  |  |
| 11220 | Primary Education | Net enrolment ratio in primary school | 51.6 | 43 | > 59.1 | tbd | EMIS | Specific contribution of HRDP programme difficult to quantify, but should lead to a slightly higher value than “without programme” |
|  |  | Gender parity index in primary education [4] | 0.933 | 0.96 | >0.955 | tbd | EMIS |  |
|  |  | Net enrolment ratio in primary schools in rural areas | n/a | n/a | n/a | n/a | - | Data not collected by Government |
|  |  | Difference in Prep to Grade 8 NER between highest and lowest districts | 57% | Awaiting data | <46.3% | tbd | EMIS | UBE Plan indicator #12 might provide a proxy indicator |

The above table shows a deterioration in pupil/teacher ratio with an increase to 34.77, a lower than expected net enrolment ratio of 43 compared to the 2010 value of 51.6 and an improved gender parity index score higher than the 2013 target. The differences in values may be explained by, for example, improved reporting of education data over recent years through the school census (Net Enrolment Ratio) and improved access to education (Pupil Teacher Ratio). However, it is unclear how any of the indicators would be specifically affected by HRDP1 other than those where no data is collected (Percentage of trainers trained).

The UBE indicators and OVI in relation to Programme Purpose require further review and will be explored in the Monitoring and Evaluation (M&E) activity of HRDP1 and Annual Education Sector Review, where UBE and HRDP1 progress will be assessed and interim targets established. To date, no assessment of UBE has taken place by GoPNG since its launch.

The Result-Area OVI are presented in section 3.1.1 Logical Framework.  Based upon the proposed activity plan above, the OVI will be as follows:

| Result-Area 1 | Result-Area 2 | Result-Area 3 |
| --- | --- | --- |
| IR1.1 At least 80% of financial reports submitted by provincial education and district education advisors are provided on time and in line with ruling requirements | IR2.1 By 2013, at least 90% of college tutors teach skills and knowledge related to pedagogy and the requirements of OBE, both in In-Service and Pre-Service Training Programmes | IR3.1 100% of student teachers sponsored by scholarships accommodated in expanded capacities at TTC (staff houses, dormitories and classrooms) by 2015 |
| IR1.2 Production of annual action plans and budgets in line with education plans (national, provincial and district) |  | IR3.2 At least 250 primary school teachers coming from remote and underserviced areas trained, 50% of which will be female |
| IR1.3 At least one Joint Sector Review conducted yearly as from 2013 |  |  |
| IR1.4 Financial, administrative and textbook indicators included in EMIS by 2015 |  |  |
| IR1.5 Percentage of PEA, DEO and inspectors having received management training reaching 100% by 2015 |  |  |
| IR1.6 Percentage of the Standard Officers (school inspectors) monitoring and reporting as per agreed upon standards increased by 10% by 2015 |  |  |
| IR1.7 Percentage of cadres at National, Regional and Provincial levels meeting the established standards regarding planning, M+E and reporting increased by 10% by 2015 |  |  |
| IR1.8 At least 2 research studies launched by local research institutions (universities) in collaboration with the Top Management Team |  |  |
| IR1.9 At least twice a year, there are inter-departmental meetings involving DoE, TSC and related Ministries and departments (especially DNPM, Finance, Treasury, Community Development, Provincial and Local Level Government Affairs [DPLLGA]) and development partners (DP) |  |  |

## Monitoring

The Beneficiary Project Supervisor, here the Secretary of Education, is overall responsible for HRDP1 monitoring. On a daily basis, the LTTA will support the designated DOE Project Manager and Component Focal Points to oversee the administrative and technical aspects of HRDP1 implementation. In relation to the LTTA Service Contract, the TL will oversee KE and NKE inputs and outputs together with the LTTA members and their DOE counterparts. Eurecna will provide backstopping.

Programme implementation, outputs and results will be discussed through the following institutional structures of the programme: ad-hoc and weekly meetings with Focal Points and designated project manager; ad-hoc and quarterly Technical Focus Group meetings; and semi-annual Steering Committee meetings.

Interim Reports of progress of the LTTA Service Contract will be completed on a six-monthly basis and short progress reports of DOE activities will be circulated on a quarterly basis, aligned with the Technical Focus Group meetings.

HRDP1 reporting will be aligned with the Annual Education Sector Review (AESR), a critical output of HRDP1. The purpose of such a mechanism is to align the various government and non-government programme and project reviews and evaluations to minimise the number of separate reviews taking place across the department on an annual basis. As such, it is hoped that annual evaluation of HRDP1 by DOE and partner stakeholders will take place during the AESR.

# Update on Assumptions and Risks

## Assumptions

The following assumptions were made during the formulation of HRDP1 and are updated here:

| ASSUMPTION | COMMENT |
| --- | --- |
| 1. GoPNG support for the sector will continue | Increased national education budget supports this assumption |
| 2. UBE Plan fully financed | This has not materialised. The UBE plans remains under-financed and given the ambitious nature of the budget looks to remain under-financed |
| 3. ESIP fully operationalized | ESIP has not become fully operationalized. HRDP1 will support the operationalization of ESIP |
| 4. The Partnership Framework and GoPNG approach to an education SWAp is flexible and allows the EU to provide support to the education sector through a variety of modalities | This assumption seems reasonable |
| 5. Political will to enhance capacities at sub-national levels | This assumption remains |
| 6. DoE remains committed to strengthening sector coordination and developing effective partnerships with government (DNPM, Finance, etc.), including those at sub-national level, civil society stakeholders and churches | This assumption remains |
| 7. DoE clearly defines OBE and its related requirements | OBE is currently under review. This assumption looks unlikely to hold |
| 8. TTC are firmly committed to decentralised training approaches | This assumption remains |
| 9. Department of Personnel Management and the Teaching Service Commission give a high priority to reducing teacher absenteeism | This assumption remains |

## Risks and flexibility

There are risks to the successful implementation of HRDP1, mainly related to the non-fulfilment of the assumptions listed above. The core risks and mitigating measures are listed below:

| RISKS | MEASURES |
| --- | --- |
| 1. Domestic PNG inflation continues to reduce the actual spending value of HRDP1 | None. Inflation must be monitored and if necessary, the programme adjusted on a periodic basis |
| 2. The weakening of the EURO continues to reduce the actual spending value of HRDP1 | None. |
| 3. The GoPNG does not take ownership of HRDP1 resulting in poor implementation and sustainability | The LTTA ensure they do not take over implementation but provide the required support for DOE leadership, implementation and ownership |
| 4. Capacity to administrate HRDP1 following EC Procedures negatively impacts HRDP1 | The LTTA provide suitable levels of support and capacity building where necessary to ensure DOE knowledge and use of EC Procedures is adequate |
| 5. DOE does not fill vacant positions within respective divisions and shortages result in insufficient staff for implementation | DOE to ensure that vacant positions are filled and officers are mandated to implement HRDP1 alongside GoPNG activity implementation |

# Planning to ensure sustainability

## Appropriate Ownership

Sustainability derives from the individuals within the system understanding, working and taking ownership of the system. The LTTA will endeavour to support DOE and other national and sub-national office personnel to lead the development process at design, development and rollout.

## Appropriate Systems and Processes

The LTTA will ensure that no ‘off-the-shelf’ system, process or tools are introduced into Papua New Guinea under HRDP1. Experience of neighbouring and distance countries in the development of their education system is important, but we will not assume what has been successful elsewhere will be successful in PNG. All proposed activities will be contextualised and thoroughly tested prior to wider implementation.

## Social Aspects

The social impact of education system development and reform is extremely high. Direct results are not only visible among civil servants but also for the general public, with education impacting upon the majority of households in the country at any time. Therefore we will focus effort on both long and short-term issues so progress is partly visible at all time.

## Programme Management Capacity

A critical issue for EDF funds is capacity of the beneficiary to manage and administrate them. EDF10 suffers from lack of capacity built under EDF9. As such, and considering the forthcoming second phase of EDF10 (HRDP2) and expected EDF11 support, the LTTA will ensure that procedures are in place and capacity is built for competent management of EC support to PNG Education Sector.

## Exit Strategy

As the programme progresses, we will identify in the Interim reports key issues related to future sustainability and we will try to make recommendations that allow the Beneficiary, Contracting Authority and other national/sub-national institutions to plan for sustainability. Each interim report will include our current thoughts on how the exit strategy should unfold. Our final exit strategy will contain detailed comments and recommendations in this regard.

See Annex I – Universal; Basic Education Plan, 2010-19

The SWAp of the Education Sector in Papua New Guinea is entitled the Education Sector Improvement Programme (ESIP). Future SWAp references will be entitled ESIP in this document.

See Annex II - Financing Agreement No PG/FED/21643

The exchange rate used for EURO/PGK is that of the European Commission (EC) for March 2012. This fixed rate is the official EC rate for HRDP1 Programme Estimate (PE) No 1 in support of Scholarships and all HRDP1 activities will follow this rate until maturity of PE No 1.

See Annex IV – Eurecna Consortium Technical Proposal

See Annex VI for indicative TOR for NKE1, NKE2 and NKE3

DOE (2007) Draft ESIP Management Manual, version 2 – Forward (p6)

The 5 TWG focus on Annual Operation and Financial Plan/Medium-Term Expenditure Framework, Performance Assessment Framework, Institutional Framework, Financial Management and Procurement Systems and Capacity Development Framework

For a detailed breakdown of each sub-activity, see Annex 3 Programme Work plan

For Committee and Focal Point Terms of Reference, see Annex X